## Dashboard Update
Solarization (Phase-II) |  | 6912 | 2024-08-28 | Monthly Update | 2024-07-01 | Solarization (Phase-II) | [7 empty] | Monthly Update | 2024-07-01
Project Status | Branches | %age | Solarization of MCB Branches (Phase-II)
Survey Completed | #REF!
Survey In Process/Hold | 0
Survey Pending | 11 | [11 empty] | tentative
Total | #REF! | 0% | [10 empty] | 2024-08-20 | 2024-07-31 | 2024-08-31
VENDOR PROGRESS | BEL | REON | PANTERA | Total | %age Completion | Installation | BEL | REON | PANTERA | Total |  | Work not started yet | bel | reon | pantera
Total Branches | 128 | 155 | 134 | 417 |  | Installation in Process | 13 | 17 | 7 | 37 | 37 | 67 | 21 | 2 | 44
Survey Completed | 128 | 155 | 134 | 417 | 100% | Installation Completed | 60 | 65 | 37 | 162 | 162
Survey In Process | 0 | 0 | 0 | 0 | 0% | Sites Commissioned | 60 | 65 | 37 | 162 | 67
Survey Pending | 0 | 0 | 0 | 0 | 0% | Live Branches (Online) | 50 | 16 | 31 | 97 | 266
[6 empty] | Net Metering | 3 | 7 | 14 | 24
Survey Completed | 128 | 155 | 134 | 417
Feasible Branches | 94 | 84 | 88 | 266 | 63.79% | INVERTER STOCK | BEL | REON | PANTERA | Stock | Issued | Balance
Eliminated Branches | 34 | 71 | 46 | 151 | 36.21% | 10-Kw | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Design Awaited | 0 | 0 | 0 | 0 | 0% | 15-Kw | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[6 empty] | 20-Kw | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Design Submitted | 94 | 84 | 88 | 266 |  | 25-Kw | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Design Approved | 94 | 84 | 88 | 266 | 100% | 50-Kw | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Under Review | 0 | 0 | 0 | 0 | 0% | 115-Kw | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[7 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Invoices | BEL (Rs.) | REON (Rs.) | PANTERA (Rs.) | AE Solar (Rs.)
Panels | 0 | 1000000 | 0 | 0 | 1000000 |  | Solar Panels |  |  |  | On Grid Inverters
Inverters |  | 5000000 |  | 0 | 5000000 | UTILIZATION | Approved Designs | Panel Stock | Utilized | Balance | 10-kW | 15-kW | 20-kW | 25-kW | 50-kW | 115-kW
Batteries |  | 0 |  | 0 | 0
Local Supplies | 0 | 200000 | 0 | 0 | 200000 | BEL | #REF! | 1800 | #REF! | #REF! | 45 | 35 | 12 | 2 | 0 | 0
Total | 0 | 6200000 | 0 | 0 | 6200000 | REON | #REF! | 2249 | #REF! | #REF! | 13 | 10 | 4 | 3 | 1 | 0
Others |  |  |  |  | 0 | PANTERA | #REF! | 2800 | #REF! | #REF! | 56 | 16 | 11 | 2 | 5 | 1
Equipment Supply | Panels | Inverters | Batteries |  |  |  | #REF! | 6849 | #REF! | #REF! | 114 | 61 | 27 | 7 | 6 | 1
BEL | 100 | 0 | 0
REON | 100 | 100 | 100
PANTERA | 100 | 0 | 0
AE Solar | 0 | 100 | 0
| 300 | 200 | 100
Utilization | (Rs. Millions)
Total Funds Approved: | 1000
Total Funds Utilized: | 72 | 7.2%
Balance Available: | 928 | 92.8%
Solarization (Phase-II) |  |  |  | Monthly Update | 2024-07-01

## Master Data
Sr. No. | Branch Code | MCB Branch Name | Owned / Rented | Region | Circle | DISCO | Vendor | Category | Survey Status | Type of System | Feasible / Eliminated | Proposal Received | Proposal Approved | System Approved by MCB | On Grid Inverter kW | Hybrid Inverter 12kW | Hybrid Inverter 8kW | No. of Panels | No. of Batteries (Hybrid) | Structure | Structure & Panel Installation | Inverter Issuance | Site Commissioned | LIVE on Portal | Net Metering | Site Inspection Status | vendor | Remarks - Site Inspection | Invoice Status (In hand / Under Process / Paid) | Payment Status
1 | 1485 | BRANCH CIRCULAR ROAD MINCHINABAD | Owned | Bahawalnagar | Bahawalpur | MEPCO | BEL | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes | In Process | Received 27-5-24 | Solar Junction | Breaker is installed | Paid 80% | 20% hold due to site inspection & net metering confirmation
2 | 488 | HAROONABAD | Owned | Bahawalnagar | Bahawalpur | MEPCO | BEL | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes |  | In Process | Received 27-5-24 | Solar Junction | Breaker is installed | Paid 80% | 20% hold due to site inspection & net metering confirmation
3 | 696 | GRAIN MARKET, GAGGOO MANDI | Owned | Bahawalnagar | Bahawalpur | MEPCO | BEL | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes |  | In Process | Received 27-5-24 | Solar Junction | Breaker is installed | Paid 80% | 20% hold due to site inspection & net metering confirmation
4 | 496 | KUTCHERY ROAD, AHMEDPUR EAST | Owned | Bahawalpur | Bahawalpur | MEPCO | BEL | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes | In Process | Received 15-Jul-2024 | Solar Junction | Breaker is installed | Paid 80% | 20% hold due to site inspection & net metering confirmation
5 | 535 | MAKHDOOM AALI | Owned | Bahawalpur | Bahawalpur | MEPCO | BEL | Cluster-2 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 18 | 0 | L2 | Completed | Yes | Yes | Yes | In Process | Received 28-6-24 | Solar Junction | Breaker is installed | Paid 80% | 20% hold due to site inspection & net metering confirmation
6 | 510 | LODHRAN | Owned | Bahawalpur | Bahawalpur | MEPCO | BEL | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes | In Process | Received 01-Aug-2024 | Al-Fateh | Breaker is installed | In hand 27-6-24 | 80% in process ( to be submitted in CAD) 20 % hold due to betmetring and inspection
7 | 616 | TALAGANG | Owned | Chakwal | Jhelum | IESCO | BEL | Cluster-3 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 18 | 0 | Elevated | Completed | Yes (re-allocated) | Yes | Yes |  | Ordered 08-Aug-2024 | Al-Fateh | Breaker is installed
8 | 1152 | DHUDIAL | Owned | Chakwal | Jhelum | IESCO | BEL | Cluster-3 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes |  | Received 06-08-2024 | Al-Fateh | Breaker is installed | In hand 27-6-24 | 80% in process ( to be submitted in CAD) 20 % hold due to betmetring and inspection
9 | 1296 | CHOA SAIDAN SHAH | Owned | Chakwal | Jhelum | IESCO | BEL | Cluster-3 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes |  | Received 06-08-2024 | Al-Fateh | Breaker is installed | In hand 27-6-24 | 80% in process ( to be submitted in CAD) 20 % hold due to betmetring and inspection
10 | 1478 | BRANCH DGK CEMENT COMPANY KHAIRPUR | Owned | Chakwal | Jhelum | IESCO | BEL | Cluster-3 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Completed | Yes (re-allocated) | Yes | Yes |  | Received 06-08-2024 | Al-Fateh | Breaker is installed
11 | 1611 | FRUIT MANDI CHAKWAL | Owned | Chakwal | Jhelum | IESCO | BEL | Cluster-3 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 20 |  |  | 18 | 0 | Elevated | In Process | Yes (re-allocated) | Commissioning in process |  |  | Ordered 08-Aug-2024 | Al-Fateh | Breaker is installed
12 | 1221 | D.G KHAN MICROWAVE TOWER | Owned | Dera Ghazi Khan | Multan | MEPCO | BEL | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 20 |  |  | 18 | 0 | Elevated | In Process | Yes | [5 empty] | Breaker is installed
13 | 1474 | Qila Didar sing | Owned | Gujranwala | Gujranwala | GEPCO | BEL | Cluster-3 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 20 |  |  | 18 | 0 | Elevated | In Process | Yes | [5 empty] | Breaker is installed
14 | 191 | Hafizbad Branch GRW | Owned | Gujranwala | Gujranwala | GEPCO | BEL | Cluster-1 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is installed
15 | 203 | Cantt | Owned | Gujranwala | Gujranwala | GEPCO | BEL | Cluster-1 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is installed
16 | 219 | Ghallamandi | Owned | Gujranwala | Gujranwala | GEPCO | BEL | Cluster-1 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is installed
17 | 189 | MCB GHAKHAR GUJRANWALA | Owned | Gujranwala | Gujranwala | GEPCO | BEL | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes | In Process | Completed & Paid | Solar Junction | Breaker is installed | Paid 80% | 20% hold due to site inspection & net metering confirmation
18 | 825 | Jalalpur Jattan | Owned | Gujrat | Sialkot | GEPCO | BEL | Cluster-4 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is installed
19 | 1297 | Kutchery Chowk Gujrat | Owned | Gujrat | Sialkot | GEPCO | BEL | Cluster-2 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes | In Process | Received 13-5-24 | Solar Junction | Breaker is installed | Paid 80% | 20% hold due to site inspection & net metering confirmation
20 | 1471 | BRANCH ALLAHABAD WAZIRABAD | Owned | Gujrat | Sialkot | GEPCO | BEL | Cluster-4 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Pending | Yes | [5 empty] | Breaker is installed
21 | 1410 | G.T. Road Gujrat | Owned | Gujrat | Sialkot | GEPCO | BEL | Cluster-2 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes | In Process | Received 13-5-24 | Solar Junction | Breaker is installed | Paid 80% | 20% hold due to site inspection & net metering confirmation
22 | 1109 | Jalalpur Sobtian | Rented | Gujrat | Sialkot | GEPCO | BEL | Cluster-4 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 18 | 0 | Elevated | Pending | Yes | [5 empty] | Breaker is installed
23 | 1004 | Village Bhaddar | Rented | Gujrat | Sialkot | GEPCO | BEL | Cluster-1 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is installed
24 | 1277 | Adda Pull 25 | Rented | Jhang | Sialkot | MEPCO | BEL | Cluster-4 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Pending | Yes | [5 empty] | Breaker is installed
25 | 586 | GUJAR KHAN | Owned | Jhelum | Jhelum | IESCO | BEL | Cluster-3 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 20 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes |  | Received 01-Aug-2024 | Al-Fateh | Breaker is installed
26 | 590 | JHELUM MAIN | Owned | Jhelum | Jhelum | IESCO | BEL | Cluster-3 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 20 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes |  | Ordered 08-Aug-2024 | Al-Fateh | Breaker is installed
27 | 595 | DINA | Owned | Jhelum | Jhelum | IESCO | BEL | Cluster-3 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 20 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes |  | Received 01-Aug-2024 | Al-Fateh | Breaker is installed | In hand 27-6-24 | 80% in process ( to be submitted in CAD) 20 % hold due to betmetring and inspection
28 | 653 | BRANCH SARAI ALAMGIR | Owned | JHELUM | Jhelum | IESCO | BEL | Cluster-3 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes |  | Ordered 08-Aug-2024 | Al-Fateh | Breaker is installed
29 | 1806 | Kutchery Road Mandi Bahauddin | Owned | Mandi Bahauddin | Sargodha | GEPCO | BEL | Cluster-3 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes |  | Received 06-08-2024 | Al-Fateh | Breaker is installed | In hand 27-6-24 | 80% in process ( to be submitted in CAD) 20 % hold due to betmetring and inspection
30 | 347 | Mandi Bahauddin | Owned | Mandi Bahauddin | Sargodha | GEPCO | BEL | Cluster-3 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes |  | Received 06-08-2024 | Al-Fateh | Breaker is installed | In hand 27-6-24 | 80% in process ( to be submitted in CAD) 20 % hold due to betmetring and inspection
31 | 440 | Barmusa | Owned | Mandi Bahauddin | Sargodha | GEPCO | BEL | Cluster-3 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes |  | Received 06-08-2024 | Al-Fateh | Breaker is installed | In hand 27-6-24 | 80% in process ( to be submitted in CAD) 20 % hold due to betmetring and inspection
32 | 1875 | Kharian-Mandi Bahauddin Road Dinga | Owned | Mandi Bahauddin | Sargodha | GEPCO | BEL | Cluster-3 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes |  | Ordered 08-Aug-2024 | Al-Fateh | Breaker is installed
33 | 257 | Verpal | Rented | Mandi Bahauddin | Sargodha | GEPCO | BEL | Cluster-4 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is installed
34 | 736 | University Road | Owned | Multan | Multan | MEPCO | BEL | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes | In Process | Received 27-5-24 | Solar Junction | Breaker is installed | Paid 80% | 20% hold due to site inspection & net metering confirmation
35 | 504 | MULTAN CANTT | Owned | Multan | Multan | MEPCO | BEL | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes | In Process | Received 27-5-24 | Solar Junction | Breaker is installed | Paid 80% | 20% hold due to site inspection & net metering confirmation
36 | 1895 | Nawabpur Road Multan | Rented | Multan | Multan | MEPCO | BEL | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 20 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes |  | Received 06-08-2024 | Al-Fateh | Breaker is installed | In hand 27-6-24 | 80% in process ( to be submitted in CAD) 20 % hold due to betmetring and inspection
37 | 528 | SHUJABAD | Owned | Muzaffargarh | Multan | MEPCO | BEL | Cluster-1 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is installed
38 | 815 | ALIPUR | Owned | Muzaffargarh | Multan | MEPCO | BEL | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 18 | 0 | Elevated | In Process | Yes | [5 empty] | Breaker is installed
39 | 503 | MUZAFFARGARH | Owned | Muzaffargarh | Multan | MEPCO | BEL | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 20 |  |  | 18 | 0 | Elevated | In Process | Yes | [5 empty] | Breaker is installed
40 | 267 | Adda Badiana | Owned | Narowal | Gujranwala | GEPCO | BEL | Cluster-3 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 18 | 0 | Elevated | In Process | Yes | [5 empty] | Breaker is installed
41 | 579 | Wadala Sandhuan | Rented | Narowal | Gujranwala | GEPCO | BEL | Cluster-3 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | In Process | Yes | Commissioning in process |  |  | Ordered 08-Aug-2024 | Al-Fateh | Breaker is installed
42 | 844 | MODEL TOWN KHANPUR | Owned | Rahim Yar Khan | Bahawalpur | MEPCO | BEL | Cluster-2 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | L2 | Completed | Yes | Yes | Yes | In Process | Received 01-Aug-2024 | Al-Fateh | Breaker is installed | In hand 27-6-24 | 80% in process ( to be submitted in CAD) 20 % hold due to betmetring and inspection
43 | 1106 | BRANCH RAHIMYAR KHAN SHAHI ROAD | Owned | Rahim yarkhan | Bahwalpur | MEPCO | BEL | Cluster-4 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is installed
44 | 539 | Sahiwal Kot Farid | Owned | Sahiwal | Sahiwal | MEPCO | BEL | Cluster-1 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is installed
45 | 833 | Sahiwal (M.C) | Owned | Sahiwal | Sahiwal | MEPCO | BEL | Cluster-2 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes | In Process | Received 27-6-24 | Solar Junction | Breaker is installed | Paid 80% | 20% hold due to site inspection & net metering confirmation
46 | 688 | Chak # 130/15-L | Owned | Sahiwal | Sahiwal | MEPCO | BEL | Cluster-2 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes | In Process | Received 27-6-24 | Solar Junction | Breaker is installed | Paid 80% | 20% hold due to site inspection & net metering confirmation
47 | 697 | KABIRWALA | Owned | Sahiwal | Sahiwal | MEPCO | BEL | Cluster-2 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes | In Process | Received 27-6-24 | Solar Junction | Breaker is installed | Paid 80% | 20% hold due to site inspection & net metering confirmation
48 | 547 | PULL 12 - MEEL | Owned | Sahiwal | Sahiwal | MEPCO | BEL | Cluster-2 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes | In Process | Received 28-6-24 | Solar Junction | Breaker is installed | Paid 80% | 20% hold due to site inspection & net metering confirmation
49 | 222 | BRANCH GOHADPUR | Owned | Sialkot | Sialkot | GEPCO | BEL | Cluster-4 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is installed
50 | 1409 | Paris Road Sialkot | Owned | Sialkot | Sialkot | GEPCO | BEL | Cluster-4 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Pending | Yes | [5 empty] | Breaker is installed
51 | 518 | PIROWAL | Owned | Vehari | Sahiwal | MEPCO | BEL | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes |  | Yes | Received 27-6-24 | Solar Junction | Breaker is installed | Paid 80% | 20% hold due to site inspection & net metering confirmation
52 | 489 | VEHARI | Owned | Vehari | Sahiwal | MEPCO | BEL | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes | In Process | Received 27-5-24 | Solar Junction | Breaker is installed | Paid 80% | 20% hold due to site inspection & net metering confirmation
53 | 494 | KHANEWAL | Owned | Vehari | Sahiwal | MEPCO | BEL | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes | Yes | Received 06-08-2024 | Al-Fateh | Breaker is installed | In hand 27-6-24 | 80% in process ( to be submitted in CAD) 20 % hold due to betmetring and inspection
54 | 493 | JAMIA BAZAR CHISHTIAN | Owned | Bahawalnagar | Bahawalpur | MEPCO | BEL | Cluster-4 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is installed
55 | 505 | Qaboola | Owned | Bahawalnagar | Bahawalpur | MEPCO | BEL | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes | In Process | Received 27-5-24 | Solar Junction | Breaker is not compliant | Paid 80% | 20% hold due to site inspection & net metering confirmation
56 | 480 | Arifwala | Owned | Bahawalnagar | Bahawalpur | MEPCO | BEL | Cluster-1 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
57 | 1476 | SATELLITE TOWN BAHAWALPUR | Owned | Bahawalpur | Bahawalpur | MEPCO | BEL | Cluster-2 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes | In Process | Received 15-Jul-2024 | Solar Junction | Breaker is not compliant | Paid 80% | 20% hold due to site inspection & net metering confirmation
58 | 497 | BAHAWALPUR GHALLA MANDI | Owned | Bahawalpur | Bahawalpur | MEPCO | BEL | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes | In Process | Received 15-Jul-2024 | Solar Junction | Breaker is not compliant | Paid 80% | 20% hold due to site inspection & net metering confirmation
59 | 512 | NOORPUR NAURANGA | Owned | Bahawalpur | Bahawalpur | MEPCO | BEL | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes | In Process | Received 15-Jul-2024 | Solar Junction | Breaker is not compliant | Paid 80% | 20% hold due to site inspection & net metering confirmation
60 | 1164 | MODEL TOWN, BAHAWALPUR | Owned | Bahawalpur | Bahawalpur | MEPCO | BEL | Cluster-2 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes | In Process | Received 15-Jul-2024 | Solar Junction | Breaker is not compliant | Paid 80% | 20% hold due to site inspection & net metering confirmation
61 | 684 | PULL DAOW | Owned | Bahawalpur | Bahawalpur | MEPCO | BEL | Cluster-2 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 20 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes | In Process | Received 28-6-24 | Solar Junction | Breaker is not compliant | Paid 80% | 20% hold due to site inspection & net metering confirmation
62 | 738 | BAHAWALPUR FARID GATE | Owned | Bahawalpur | Bahawalpur | MEPCO | BEL | Cluster-2 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 25 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes |  |  | Received 01-Aug-2024 | Al-Fateh | Breaker is not compliant | In hand 27-6-24 | 80% in process ( to be submitted in CAD) 20 % hold due to betmetring and inspection
63 | 1375 | SUI WALA | Rented | Bahawalpur | Bahawalpur | MEPCO | BEL | Cluster-2 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes |  | In Process | Received 27-6-24 | Solar Junction | Breaker is not compliant | Paid 80% | 20% hold due to site inspection & net metering confirmation
64 | 524 | MUHAMMADPUR | Owned | Dera Ghazi Khan | Multan | MEPCO | BEL | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 18 | 0 | Elevated | In Process | Yes | [5 empty] | Breaker is not compliant
65 | 499 | D.G KHAN Katchery Road | Owned | Dera Ghazi Khan | Multan | MEPCO | BEL | Cluster-1 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
66 | 1424 | Sheikhupura Road | Owned | Gujranwala | Gujranwala | GEPCO | BEL | Cluster-3 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 25 |  |  | 18 | 0 | Elevated | In Process | Yes | [5 empty] | Breaker is not compliant
67 | 1460 | Jalalpur Bhattian | Owned | Gujranwala | Gujranwala | GEPCO | BEL | Cluster-3 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 20 |  |  | 18 | 0 | Elevated | In Process | Yes | [5 empty] | Breaker is not compliant
68 | 1034 | Jinnah Road Gujranwala | Owned | Gujranwala | Gujranwala | GEPCO | BEL | Cluster-1 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
69 | 1209 | MODEL TOWN BRANCH | Owned | Gujranwala | Gujranwala | GEPCO | BEL | Cluster-1 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
70 | 1208 | G.T ROAD GUJRANWALA | Owned | Gujranwala | Gujranwala | GEPCO | BEL | Cluster-1 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
71 | 249 | QILA MIAN SINGH | Rented | Gujranwala | Gujranwala | GEPCO | BEL | Cluster-4 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
72 | 1564 | Peoples Colony Branch Grw | Rented | Gujranwala | Gujranwala | GEPCO | BEL | Cluster-1 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
73 | 196 | Railway Road Wazirabad | Owned | Gujrat | Sialkot | GEPCO | BEL | Cluster-2 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes |  | In Process | Received 13-5-24 | Solar Junction | Breaker is not compliant | Paid 80% | 20% hold due to site inspection & net metering confirmation
74 | 274 | Bhagowal Kalan | Owned | Gujrat | Sialkot | GEPCO | BEL | Cluster-4 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
75 | 1531 | Bhimber Road, Gujrat | Owned | Gujrat | Sialkot | GEPCO | BEL | Cluster-2 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 20 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes |  |  | Received 06-08-2024 | Al-Fateh | Breaker is not compliant | In hand 27-6-24 | 80% in process ( to be submitted in CAD) 20 % hold due to betmetring and inspection
76 | 200 | Circular Road Gujrat | Owned | Gujrat | Sialkot | GEPCO | BEL | Cluster-2 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes | In Process | Received 13-5-24 | Solar Junction | Breaker is not compliant | Paid 80% | 20% hold due to site inspection & net metering confirmation
77 | 1778 | Village Saboor Sharif | Rented | Gujrat | Sialkot | GEPCO | BEL | Cluster-4 | Completed | On-Grid | Eliminated |  |  | 10.26 |  |  |  | 18 | 0 | Elevated | [7 empty] | Breaker is not compliant
78 | 1620 | Service More, G.T. Road Gujrat | Rented | Gujrat | Sialkot | GEPCO | BEL | Cluster-2 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | L2 | Completed | Yes | Yes |  | In Process | Received 13-5-24 | Solar Junction | Breaker is not compliant | Paid 80% | 20% hold due to site inspection & net metering confirmation
79 | 4038 | Kuri Sharif | Rented | Gujrat | Sialkot | GEPCO | BEL | Cluster-2 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | L2 | Completed | Yes | Yes | Yes | In Process | Received 13-5-24 | Solar Junction | Breaker is not compliant | Paid 80% | 20% hold due to site inspection & net metering confirmation
80 | 8008 | Sialkot Road Wazirabad | Rented | Gujrat | Sialkot | GEPCO | BEL | Cluster-2 | Completed | On-Grid | Eliminated |  |  | 10.26 | [7 empty] | No - shifted to 0014 | [5 empty] | Breaker is not compliant
81 | 1845 | Gulyana | Rented | Gujrat | Sialkot | GEPCO | BEL | Cluster-1 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
82 | 4013 | Sadwal Kalan | Rented | Gujrat | Sialkot | GEPCO | BEL | Cluster-4 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Pending | Yes | [5 empty] | Breaker is not compliant
83 | 1417 | Kotla Arab Ali Khan | Rented | Gujrat | Sialkot | GEPCO | BEL | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Pending | Yes | [5 empty] | Breaker is not compliant
84 | 1385 | Doga Tehal | Rented | Gujrat | Sialkot | GEPCO | BEL | Cluster-2 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 18 | 0 | Elevated | In Process | Yes | [5 empty] | Breaker is not compliant
85 | 192 | Lalamusa | Rented | Gujrat | Sialkot | GEPCO | BEL | Cluster-2 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes |  |  | Received 06-08-2024 | Al-Fateh | Breaker is not compliant | In hand 27-6-24 | 80% in process ( to be submitted in CAD) 20 % hold due to betmetring and inspection
86 | 260 | Railway Road Gujrat | Rented | Gujrat | Sialkot | GEPCO | BEL | Cluster-2 | Completed | On-Grid | Eliminated |  |  | 10.26 | [7 empty] | No - shifted to 0616 | [5 empty] | Breaker is not compliant
87 | 879 | Village Panjan Kissana | Rented | Gujrat | Sialkot | GEPCO | BEL | Cluster-1 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
88 | 4034 | Wapda Town Phase II Multan | Rented | Multan | Multan | MEPCO | BEL | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes | In Process | Received 27-5-24 | Solar Junction | Breaker is not compliant | Paid 80% | 20% hold due to site inspection & net metering confirmation
89 | 490 | KOT ADDU | Owned | Muzaffargarh | Multan | MEPCO | BEL | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 18 | 0 | Elevated | In Process | Yes | [5 empty] | Breaker is not compliant
90 | 827 | Narowal | Rented | Narowal | Gujranwala | GEPCO | BEL | Cluster-4 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Pending | Yes | [5 empty] | Breaker is not compliant
91 | 485 | SADIQ BAZAR RAHIM YAR KHAN MAIN | Owned | Rahim Yar Khan | Bahawalpur | MEPCO | BEL | Cluster-2 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes | In Process | Received 27-5-24 | Solar Junction | Breaker is not compliant | Paid 80% | 20% hold due to site inspection & net metering confirmation
92 | 482 | Mian Channu | Owned | Sahiwal | Sahiwal | MEPCO | BEL | Cluster-2 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes | In Process | Received 28-6-24 | Solar Junction | Breaker is not compliant | Paid 80% | 20% hold due to site inspection & net metering confirmation
93 | 509 | Sahiwal (G.M.) | Owned | Sahiwal | Sahiwal | MEPCO | BEL | Cluster-2 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes | In Process | Received 28-6-24 | Solar Junction | Breaker is not compliant | Paid 80% | 20% hold due to site inspection & net metering confirmation
94 | 258 | Ghuinke | Owned | Sialkot | Sialkot | GEPCO | BEL | Cluster-4 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
95 | 1043 | Dara Araiyan Sialkot | Owned | Sialkot | Sialkot | GEPCO | BEL | Cluster-4 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 18 | 0 | Elevated | Pending | Yes | [5 empty] | Breaker is not compliant
96 | 241 | Kullowal Road Sialkot | Owned | Sialkot | Sialkot | GEPCO | BEL | Cluster-4 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
97 | 685 | GARAH MORE, VEHARI | Owned | Vehari | Sahiwal | MEPCO | BEL | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes | In Process | Received 27-5-24 | Solar Junction | Breaker is not compliant | Paid 80% | 20% hold due to site inspection & net metering confirmation
98 | 994 | ADDA PAKHI MORE | Owned | Vehari | Sahiwal | MEPCO | BEL | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes |  | In Process | Received 27-5-24 | Solar Junction | Breaker is not compliant | Paid 80% | 20% hold due to site inspection & net metering confirmation
99 | 511 | PULL-14 | Owned | Vehari | Sahiwal | MEPCO | BEL | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes | Yes | Received 27-5-24 | Solar Junction | Breaker is not compliant | Paid 80% | 20% hold due to site inspection & net metering confirmation
100 | 1547 | COLLEGE ROAD BUREWALA | Owned | Vehari | Sahiwal | MEPCO | BEL | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 20 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes | In Process | Received 27-5-24 | Solar Junction | Breaker is not compliant | Paid 80% | 20% hold due to site inspection & net metering confirmation
101 | ABEP-2023-1 | Circular Road Narowal | Rented | Narowal | Faisalabad | GEPCO | BEL | Cluster-4 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
102 | ABEP-2023-2 | Qila Kalar Wala | Rented | Narowal | Faisalabad | GEPCO | BEL | Cluster-4 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
103 | 395 | Pinanwal | Rented | Chakwal | Jhelum | IESCO | BEL | Cluster-3 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes |  | Ordered 08-Aug-2024 | Al-Fateh | Breaker is not compliant
104 | 603 | Chakwal Main | Rented | Chakwal | Jhelum | IESCO | BEL | Cluster-3 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes |  | Received 06-08-2024 | Al-Fateh | Breaker is not compliant
105 | 626 | Kallar Kahar | Rented | Chakwal | Jhelum | IESCO | BEL | Cluster-3 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes |  | Received 06-08-2024 | Al-Fateh | Breaker is not compliant
106 | 632 | Mulhal Mughlan | Rented | Chakwal | Jhelum | IESCO | BEL | Cluster-3 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | In Process | Yes | Commissioning in process |  |  | Ordered 08-Aug-2024 | Al-Fateh | Breaker is not compliant
107 | 646 | Bhaun | Rented | Chakwal | Jhelum | IESCO | BEL | Cluster-3 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes |  | Received 06-08-2024 | Al-Fateh | Breaker is not compliant | In hand 27-6-24 | 80% in process ( to be submitted in CAD) 20 % hold due to betmetring and inspection
108 | 1177 | Thaneel Fatuhi | Rented | Chakwal | Jhelum | IESCO | BEL | Cluster-3 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes |  | Received 06-08-2024 | Al-Fateh | Breaker is not compliant
109 | 1507 | Village Munara | Rented | Chakwal | Jhelum | IESCO | BEL | Cluster-3 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes |  | Ordered 08-Aug-2024 | Al-Fateh | Breaker is not compliant
110 | 656 | Village Nakoodar | Rented | Mirpur A.K. | Jhelum | IESCO | BEL | Cluster-4 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Pending | Yes | [5 empty] | Breaker is not compliant
111 | 625 | Choha Khalsa | Rented | Rawalpindi Cantt | Islamabad | IESCO | BEL | Cluster-4 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Pending | To be Issued | [5 empty] | Breaker is not compliant
112 | 650 | Kallar Syedan | Rented | Rawalpindi Cantt | Islamabad | IESCO | BEL | Cluster-4 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 18 | 0 | Elevated | Pending | To be Issued | [5 empty] | Breaker is not compliant
113 | 1280 | Sihal | Rented | Rawalpindi Cantt | Islamabad | IESCO | BEL | Cluster-4 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Pending | Yes | [5 empty] | Breaker is not compliant
114 | 681 | Chowk Shah Abbas Multan | Owned | Multan | Multan | MEPCO | BEL | Cluster-4 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 18 | 0 | L2 | Pending | To be Issued | [5 empty] | Breaker is not compliant
115 | 699 | Fort Abbas | Owned | Bahawalnagar | Bahawalpur | MEPCO | BEL | Cluster-4 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
116 | 807 | KLP Road Sadiqabad | Owned | Rahim Yar Khan | Bahawalpur | MEPCO | BEL | Cluster-4 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 18 | 0 | Elevated | Pending | Yes | [5 empty] | Breaker is not compliant
117 | 1401 | MCB DHA | Owned | Lahore Defence | Lahore East | LESCO | Pantera | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes | Yes | Completed & Paid | Solar Junction | Breaker is not compliant | Paid | 20% payment with 80% advance settlement
118 | 1496 | Khayaban-e Iqbal Walton Road | Owned | Lahore Defence | Lahore East | LESCO | Pantera | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes | Yes | Completed & Paid | Solar Junction | Breaker is not compliant | Paid | 20% payment with 80% advance settlement
119 | 1879 | DHA Phase I G-Block | Owned | Lahore Defence | Lahore East | LESCO | Pantera | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes | Yes | Completed & Paid | Solar Junction | Breaker is not compliant | Paid | 20% payment with 80% advance settlement
120 | 1508 | Cavalry Ground | Owned | Lahore Defence | Lahore East | LESCO | Pantera | Cluster-1 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
121 | 1575 | DHA Phase 5 | Owned | Lahore Defence | Lahore East | LESCO | Pantera | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes | Yes | Completed & Paid | Solar Junction | Breaker is not compliant | Paid | 20% payment with 80% advance settlement
122 | 1699 | DHA Phase 6 | Owned | Lahore Defence | Lahore East | LESCO | Pantera | Cluster-1 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
123 | 1803 | DHA Phase 8 | Owned | Lahore Defence | Lahore East | LESCO | Pantera | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes | Yes | Completed & Paid | Solar Junction | Breaker is not compliant | Paid | 20% payment with 80% advance settlement
124 | 1388 | DHA Z Block | Owned | Lahore Defence | Lahore East | LESCO | Pantera | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 20 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes | Yes | Completed & Paid | Solar Junction | Breaker is not compliant | Paid | 20% payment with 80% advance settlement
125 | 214 | Railway Road,Kasur | Owned | Lahore Gulberg | Lahore East | LESCO | Pantera | Cluster-2 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | In Process | Yes |  | In Progress |  |  |  | Breaker is not compliant
126 | 1258 | Kahna Br. Lahore | Owned | Lahore Gulberg | Lahore East | LESCO | Pantera | Cluster-1 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
127 | 183 | Mian Market Gulberg | Owned | Lahore Gulberg | Lahore East | LESCO | Pantera | Cluster-1 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
128 | 1400 | LAHORE PREMIER | Owned | Lahore Gulberg | Lahore East | LESCO | Pantera | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 20 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes |  | Received 25-6-24 | Solar Junction | Breaker is not compliant | Deposit in CAD | 20% supplies - Approval CTs awaited
129 | 1273 | Firdous Market, Gulberg-III Lahore | Owned | Lahore Gulberg | Lahore East | LESCO | Pantera | Cluster-1 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
130 | 1711 | Main Boulavard Gulberg, Lahore. | Owned | Lahore Gulberg | Lahore East | LESCO | Pantera | Cluster-1 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
131 | 1805 | EME DHA Lahore | Owned | Lahore Johar Town | Lahore East | DHA EME LHR | Pantera | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | In Process | Yes | [5 empty] | Breaker is not compliant
132 | 1744 | Bahria Town Lahore | Owned | Lahore Johar Town | Lahore East | Bahria Town LHR | Pantera | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | In Process | Yes | [5 empty] | Breaker is not compliant
133 | 1302 | Thokar Niaz Baig | Owned | Lahore Johar Town | Lahore East | LESCO | Pantera | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes | Yes | Received 25-6-24 | Solar Junction | Breaker is not compliant | Paid | 20% payment with 80% advance settlement
134 | 1403 | Faisal Town Lahore | Owned | Lahore Johar Town | Lahore East | LESCO | Pantera | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes |  | Completed & Paid | Solar Junction | Breaker is not compliant | Deposit in CAD | 20% supplies - Approval CTs awaited
135 | 1633 | Valencia Town, Lahore | Owned | Lahore Johar Town | Lahore East | Valencia Town LHR | Pantera | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 25 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes |  | Received 25-6-24 | Solar Junction | Breaker is not compliant | Deposit in CAD | 20% supplies - Approval CTs awaited
136 | 888 | Township Lahore | Owned | Lahore Johar Town | Lahore East | LESCO | Pantera | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 50 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes | Yes | Received 25-6-24 | Solar Junction | Breaker is not compliant | Paid | 20% payment with 80% advance settlement
137 | 992 | LAHORE DHARAMPURA | Owned | Lahore The Mall | Lahore West | LESCO | Pantera | Cluster-2 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Pending | Yes | [5 empty] | Breaker is not compliant
138 | 947 | LAHORE FATIMA JINNAH ROAD | Owned | Lahore The Mall | Lahore West | LESCO | Pantera | Cluster-1 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
139 | 1047 | CHOWK MAYO HOSPITAL LAHORE | Owned | Lahore The Mall | Lahore West | LESCO | Pantera | Cluster-1 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
140 | 179 | LAHORE ANARKALI | Owned | Lahore The Mall | Lahore West | LESCO | Pantera | Cluster-1 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
141 | 184 | LAHORE MCLEOD ROAD | Owned | Lahore The Mall | Lahore West | LESCO | Pantera | Cluster-1 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
142 | 1322 | DAVIS ROAD LAHORE | Owned | Lahore The Mall | Lahore West | LESCO | Pantera | Cluster-1 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
143 | 776 | LAHORE SHADMAN COLONY | Owned | Lahore The Mall | Lahore West | LESCO | Pantera | Cluster-1 | Completed | On-Grid | Eliminated |  |  | 10.26 | [5 empty] | Elevated | [7 empty] | Breaker is not compliant
144 | 5492 | HR OFFICE - LAHORE SHADMAN COLONY | Owned | Lahore The Mall | Lahore West | LESCO | Pantera | Cluster-1 | Completed | On-Grid | Eliminated |  |  | 10.26 | [5 empty] | Elevated | [7 empty] | Breaker is not compliant
145 | 176 | LAHORE NILA GUMBAD | Owned | Lahore The Mall | Lahore West | LESCO | Pantera | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 50 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes |  | Received 25-6-24 | Solar Junction | Breaker is not compliant | Deposit in CAD | 20% supplies - Approval CTs awaited
146 | 1546 | Makkuana Chowk Faisalabad | Rented | Faisalabad | Faisalabad | FESCO | Pantera | Cluster-3 Advance | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Pending | Yes | [5 empty] | Breaker is not compliant
147 | 995 | Peoples Colony Faisalabad | Owned | Faisalabad | Faisalabad | FESCO | Pantera | Cluster-3 Advance | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 50 |  |  | 18 | 0 | Elevated | Pending | Yes | [5 empty] | Breaker is not compliant
148 | 373 | Satiana Road Faisalabad | Owned | Faisalabad | Faisalabad | FESCO | Pantera | Cluster-3 Advance | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Pending | Yes | [5 empty] | Breaker is not compliant
149 | 450 | Dasuha | Rented | Faisalabad | Faisalabad | FESCO | Pantera | Cluster-3 Advance | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 18 | 0 | Elevated | Pending | Yes | [5 empty] | Breaker is not compliant
150 | 1335 | Millat Colony Faisalabad | Owned | Faisalabad | Faisalabad | FESCO | Pantera | Cluster-3 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
151 | 1479 | Village Bucheki | Rented | Faisalabad | Faisalabad | LESCO | Pantera | Cluster-2 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Pending | Yes | [5 empty] | Breaker is not compliant
152 | 1634 | Roshanwala, Faisalabad | Rented | Faisalabad | Faisalabad | FESCO | Pantera | Cluster-3 Advance | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 18 | 0 | Elevated | Pending | Yes | [5 empty] | Breaker is not compliant
153 | 1040 | Dhudiwala Faisalabad | Owned | Faisalabad | Faisalabad | FESCO | Pantera | Cluster-3 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
154 | 328 | Ghulam Muhammed Abad | Owned | Faisalabad City | Faisalabad | FESCO | Pantera | Cluster-3 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
155 | 329 | Gole Kiryana Faisalabad | Owned | Faisalabad City | Faisalabad | FESCO | Pantera | Cluster-3 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
156 | 451 | Madina Town Faisalabad | Owned | Faisalabad City | Faisalabad | FESCO | Pantera | Cluster-3 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
157 | 391 | Abdullahpur Faisalabad | Owned | Faisalabad City | Faisalabad | FESCO | Pantera | Cluster-3 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
158 | 1021 | Mansoorabad Faisalabad | Owned | Faisalabad City | Faisalabad | FESCO | Pantera | Cluster-3 Advance | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Pending | Yes | [5 empty] | Breaker is not compliant
159 | 437 | Bhowana Bazar Faisalabad | Owned | Faisalabad City | Faisalabad | FESCO | Pantera | Cluster-3 Advance | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Pending | Yes | [5 empty] | Breaker is not compliant
160 | 224 | Hafizabad Road GRW | Owned | Gujranwala | Gujranwala | GEPCO | Pantera | Cluster-3 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
161 | 4008 | Nishat Dairy Branch | Owned | Gujranwala | Gujranwala | GEPCO | Pantera | Cluster-3 Advance | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 20 |  |  | 18 | 0 | Elevated | Pending | Yes | [5 empty] | Breaker is not compliant
162 | 228 | Karrianwala | Owned | Gujrat | Sialkot | GEPCO | Pantera | Cluster-2 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Pending | Yes | [5 empty] | Breaker is not compliant
163 | 446 | Wara Thatta | Rented | Jhang | Sialkot | FESCO | Pantera | Cluster-3 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
164 | 406 | Kaki Nau | Owned | Jhang | Sialkot | FESCO | Pantera | Cluster-3 Advance | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Pending | To be Issued | [5 empty] | Breaker is not compliant
165 | 355 | Bhowana | Owned | Jhang | Sialkot | FESCO | Pantera | Cluster-3 Advance | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 18 | 0 | Elevated | Pending | Yes | [5 empty] | Breaker is not compliant
166 | 1118 | Bhakkar Road Jhang Saddar | Owned | Jhang | Sialkot | FESCO | Pantera | Cluster-3 Advance | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 20 |  |  | 18 | 0 | Elevated | Pending | Yes | [5 empty] | Breaker is not compliant
167 | 335 | Nawaz Chowk Jhang Saddar | Owned | Jhang | Sialkot | FESCO | Pantera | Cluster-3 Advance | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 20 |  |  | 18 | 0 | Elevated | Pending | Yes | [5 empty] | Breaker is not compliant
168 | 1097 | Gojra Road Jhang Saddar | Owned | Jhang | Sialkot | FESCO | Pantera | Cluster-3 Advance | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Pending | Yes | [5 empty] | Breaker is not compliant
169 | 1329 | Faisalabad Road Chiniot | Owned | Jhang | Sialkot | FESCO | Pantera | Cluster-3 Advance | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 20 |  |  | 18 | 0 | Elevated | Pending | Yes | [5 empty] | Breaker is not compliant
170 | 419 | Ghalla Mandi Toba Road Jhang Saddar | Owned | Jhang | Sialkot | FESCO | Pantera | Cluster-3 Advance | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Pending | Yes | [5 empty] | Breaker is not compliant
171 | 1030 | Ayub Chowk Jhang Saddar | Owned | Jhang | Sialkot | FESCO | Pantera | Cluster-3 Advance | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 50 |  |  | 18 | 0 | Elevated | Pending | Yes | [5 empty] | Breaker is not compliant
172 | 213 | Azam Cloth | Owned | Lahore City | Lahore West | LESCO | Pantera | Cluster-3 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
173 | 180 | Badami Bagh | Owned | Lahore City | Lahore West | LESCO | Pantera | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes |  | Completed & Paid | Solar Junction | Breaker is not compliant | Deposit in CAD | 20% supplies - Approval CTs awaited
174 | 187 | Timber Market | Owned | Lahore City | Lahore West | LESCO | Pantera | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 20 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes |  | Received 25-6-24 | Solar Junction | Breaker is not compliant | Deposit in CAD | 20% supplies - Approval CTs awaited
175 | 1423 | Chowk Gujjar pura | Owned | Lahore City | Lahore West | LESCO | Pantera | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes |  | Completed & Paid | Solar Junction | Breaker is not compliant |  | Invoice in Hand 20% supplies - Approval CTs awaited
176 | 178 | Circular Road | Owned | Lahore City | Lahore West | LESCO | Pantera | Cluster-2 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes |  | Ordered 08-Aug-2024 | Al-Fateh | Breaker is not compliant
177 | 271 | Vandala Road | Owned | Lahore City | Lahore West | LESCO | Pantera | Cluster-3 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
178 | 217 | Fruit Market | Owned | Lahore City | Lahore West | LESCO | Pantera | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes | Yes | Completed & Paid | Solar Junction | Breaker is not compliant | Paid | 20% payment with 80% advance settlement
179 | 954 | Karim Park | Owned | Lahore City | Lahore West | LESCO | Pantera | Cluster-2 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
180 | 1659 | Canal View | Owned | Lahore Multan Road | Lahore West | LESCO | Pantera | Cluster-2 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes |  | Received 01-Aug-2024 | Al-Fateh | Breaker is not compliant | In hand 25-6-24
181 | 1317 | Session Court Lahore | Owned | Lahore Multan Road | Lahore West | LESCO | Pantera | Cluster-2 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes |  | Received 01-Aug-2024 | Al-Fateh | Breaker is not compliant | In hand 25-6-24
182 | 1048 | Wahdat Road | Owned | Lahore Multan Road | Lahore West | LESCO | Pantera | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes | Yes | Completed & Paid | Solar Junction | Breaker is not compliant | Paid | 20% payment with 80% advance settlement
183 | 1210 | Mozang Road | Owned | Lahore Multan Road | Lahore West | LESCO | Pantera | Cluster-1 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
184 | 1402 | Karim Block (A.I.Town) | Owned | Lahore Multan Road | Lahore West | LESCO | Pantera | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Pending | Yes | Received 01-Aug-2024 | Al-Fateh | Breaker is not compliant
185 | 1433 | Gulshan-e-Ravi | Owned | Lahore Multan Road | Lahore West | LESCO | Pantera | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes |  | Received 25-6-24 | Solar Junction | Breaker is not compliant |  | Invoice in Hand 20% supplies - Approval CTs awaited
186 | 1354 | Allama Iqbal Town | Owned | Lahore Multan Road | Lahore West | LESCO | Pantera | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 20 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes |  | Received 25-6-24 | Solar Junction | Breaker is not compliant | Deposit in CAD | 20% supplies - Approval CTs awaited
187 | 902 | Samanabad | Owned | Lahore Multan Road | Lahore West | LESCO | Pantera | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes | Yes | Completed & Paid | Solar Junction | Breaker is not compliant | Paid | 20% payment with 80% advance settlement
188 | 364 | Piplan | Owned | Mianwali | Sargodha | FESCO | Pantera | Cluster-3 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
189 | 211 | Narang Mandi | Rented | Narowal | Gujranwala | LESCO | Pantera | Cluster-2 | Completed | On-Grid | Feasible | yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Pending | Yes | [5 empty] | Breaker is not compliant
190 | 1723 | Chora Rajpootan | Rented | Narowal | Gujranwala | LESCO | Pantera | Cluster-2 | Completed | On-Grid | Eliminated |  |  | 10.26 | [7 empty] | No - shifted to 1478 | [5 empty] | Breaker is not compliant
191 | 194 | OKARA RAVI ROAD | Owned | Okara | Sahiwal | LESCO | Pantera | Cluster-2 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
192 | 240 | CHUNIAN | Owned | Okara | Sahiwal | LESCO | Pantera | Cluster-2 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | In Process | Yes |  | In Progress |  |  |  | Breaker is not compliant
193 | 238 | MANDI AHMADABAD | Rented | Okara | Sahiwal | LESCO | Pantera | Cluster-2 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
194 | 243 | SHAM KOT NAU | Rented | Okara | Sahiwal | LESCO | Pantera | Cluster-2 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | In Process | Yes |  | In Progress |  |  |  | Breaker is not compliant
195 | 199 | Pattoki | Owned | Okara | Sahiwal | LESCO | Pantera | Cluster-2 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Pending | Yes | [5 empty] | Breaker is not compliant
196 | 770 | OKARA M.A.JINNAH | Owned | Okara | Sahiwal | LESCO | Pantera | Cluster-2 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
197 | 1535 | Sahiwal Distt. Sargodha | Owned | Sargodha | Sargodha | FESCO | Pantera | Cluster-3 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
198 | 1310 | Eid Gah Road Sargodha | Owned | Sargodha | Sargodha | FESCO | Pantera | Cluster-3 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
199 | 705 | Lak | Owned | Sargodha | Sargodha | FESCO | Pantera | Cluster-2 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | In Progress |  | Ordered 08-Aug-2024 | Solar Junction | Breaker is not compliant
200 | 385 | Lalliani | Owned | Sargodha | Sargodha | FESCO | Pantera | Cluster-2 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes |  | Ordered 08-Aug-2024 | Solar Junction | Breaker is not compliant
201 | 354 | Shahpur Saddar | Owned | Sargodha | Sargodha | FESCO | Pantera | Cluster-2 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | In Progress |  | Received 01-Aug-2024 | Al-Fateh | Breaker is not compliant
202 | 1188 | University Road Sargodha | Owned | Sargodha | Sargodha | FESCO | Pantera | Cluster-2 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 20 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes |  | Received 01-Aug-2024 | Al-Fateh | Breaker is not compliant
203 | 336 | Liaquat Market Sargodha | Owned | Sargodha | Sargodha | FESCO | Pantera | Cluster-2 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 25 |  |  | 18 | 0 | Elevated | In Process | Yes | Commissioning in Process | In Progress |  | Ordered 08-Aug-2024 | Solar Junction | Breaker is not compliant
204 | 360 | Warburton | Owned | Sheikhupura | Gujranwala | LESCO | Pantera | Cluster-2 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Pending | Yes | [5 empty] | Breaker is not compliant
205 | 1881 | Sheraz Garden Sheikhupura | Owned | Sheikhupura | Gujranwala | LESCO | Pantera | Cluster-2 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | In Progress |  | Received 01-Aug-2024 | Al-Fateh | Breaker is not compliant | In hand 25-6-24
206 | 204 | Sheikhupura Main | Owned | Sheikhupura | Gujranwala | LESCO | Pantera | Cluster-2 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | In Progress |  | Received 01-Aug-2024 | Al-Fateh | Breaker is not compliant | In hand 25-6-24
207 | 193 | Muridke | Owned | Sheikhupura | Gujranwala | LESCO | Pantera | Cluster-2 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 20 |  |  | 18 | 0 | Elevated | In Process | Yes |  | In Progress |  |  |  | Breaker is not compliant
208 | 1790 | Safdarabad | Owned | Sheikhupura | Gujranwala | LESCO | Pantera | Pending |  | On-Grid |  |  |  | 10.26 | [13 empty] | Breaker is not compliant
209 | 1489 | Waghi Adda | Rented | Toba Tek Singh | Faisalabad | FESCO | Pantera | Cluster-3 Advance | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Pending | Yes | [5 empty] | Breaker is not compliant
210 | 1738 | Samundri Faisalabad Road | Rented | Toba Tek Singh | Faisalabad | FESCO | Pantera | Cluster-3 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
211 | 758 | Sarabah Chak 336-GB | Owned | Toba Tek Singh | Faisalabad | FESCO | Pantera | Cluster-3 Advance | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Pending | Yes | [5 empty] | Breaker is not compliant
212 | 398 | Torianwala Adda | Rented | Toba Tek Singh | Faisalabad | FESCO | REON | Cluster-4 | Completed | Hybrid | Feasible | Yes | Yes | 10.26 |  | 0 | 1 | 17.8435 | 2 | Elevated | Completed | Hybrid | Yes |  |  | Ordered 08-Aug-2024 | Al-Fateh | Breaker is not compliant
213 | 382 | Khidderwala Adda | Owned | Toba Tek Singh | Faisalabad | FESCO | Pantera | Cluster-3 Advance | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Pending | Yes | [5 empty] | Breaker is not compliant
214 | 1583 | More Chak 330/GB Khikha | Rented | Toba Tek Singh | Faisalabad | FESCO | Pantera | Cluster-3 Advance | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 18 | 0 | Elevated | Pending | Yes | [5 empty] | Breaker is not compliant
215 | 353 | Rajana | Owned | Toba Tek Singh | Faisalabad | FESCO | Pantera | Cluster-3 Advance | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 18 | 0 | Elevated | Pending | Yes | [5 empty] | Breaker is not compliant
216 | 4006 | Painsara Road Gojra | Rented | Toba Tek Singh | Faisalabad | FESCO | Pantera | Cluster-3 Advance | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 18 | 0 | Elevated | Pending | Yes | [5 empty] | Breaker is not compliant
217 | 1654 | Kamalia Chichawatni Road | Rented | Toba Tek Singh | Faisalabad | FESCO | Pantera | Cluster-3 Advance | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Pending | Yes | [5 empty] | Breaker is not compliant
218 | 181 | Baghbanpura Lahore | Rented | Lahore City | Lahore West | LESCO | Pantera | Cluster-2 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Pending | Yes | [5 empty] | Breaker is not compliant
219 | 1213 | Daroghawala Lahore | Rented | Lahore City | Lahore West | LESCO | Pantera | Cluster-2 | Completed | On-Grid | Eliminated |  |  | 10.26 | [7 empty] | No - shifted to 0075 | [5 empty] | Breaker is not compliant
220 | 1468 | M-Block DHA Phase-I Lahore | Rented | Lahore Defence | Lahore East | LESCO | Pantera | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes | Yes | Completed & Paid | Solar Junction | Breaker is not compliant | Paid | 20% payment with 80% advance settlement
221 | 1008 | Gulab Devi Hospital Lahore | Rented | Lahore Gulberg | Lahore East | LESCO | Pantera | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes |  | Completed & Paid | Solar Junction | Breaker is not compliant | Deposit in CAD | 20% supplies - Approval CTs awaited
222 | 1603 | Asif Town Lahore | Rented | Lahore Gulberg | Lahore East | LESCO | Pantera | Cluster-1 | Completed | On-Grid | Eliminated |  |  | 10.26 | [5 empty] | Elevated | [7 empty] | Breaker is not compliant
223 | 1645 | Liaquat Road Kasur | Rented | Lahore Gulberg | Lahore East | LESCO | REON | Cluster-2 | Completed | Hybrid | Feasible | Yes | Yes | 10.26 |  | 1 |  | 17.8435 | 1 | Elevated | In Process | Hybrid - Returned to IT Warehouse | [5 empty] | Breaker is not compliant
224 | 1786 | Fruit & Vegetable Market Kacha Lahore | Rented | Lahore Gulberg | Lahore East | LESCO | Pantera | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Pending | Yes | Received 25-6-24 | Solar Junction | Breaker is not compliant | Paid | 20% payment with 80% advance settlement
225 | 1816 | Khudian Branch Kasur | Rented | Lahore Gulberg | Lahore East | LESCO | Pantera | Cluster-2 | Completed | On-Grid | Eliminated |  |  | 10.26 | [7 empty] | No - shifted to 0025 | [5 empty] | Breaker is not compliant
226 | 1613 | Kot Radha Kishan | Rented | Lahore Johar Town | Lahore East | LESCO | Pantera | Pending |  | On-Grid |  |  |  | 10.26 | [13 empty] | Breaker is not compliant
227 | 854 | District Courts Lahore | Rented | Lahore Multan Road | Lahore West | LESCO | Pantera | Cluster-1 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
228 | 1227 | Rewaz Garden Lahore | Rented | Lahore Multan Road | Lahore West | LESCO | Pantera | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes |  | Received 25-6-24 | Solar Junction | Breaker is not compliant | Deposit in CAD | 20% supplies - Approval CTs awaited
229 | 1831 | Chungi Multan Road | Rented | Lahore Multan Road | Lahore West | LESCO | Pantera | Cluster-3 Advance | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Pending | To be Issued | [5 empty] | Breaker is not compliant
230 | 384 | Nia Lahore | Rented | Toba Tek Singh | Faisalabad | FESCO | Pantera | Cluster-3 Advance | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Pending | To be Issued | [5 empty] | Breaker is not compliant
231 | 4079 | Adda Kalera | Rented | Toba Tek Singh | Faisalabad | FESCO | Pantera | Cluster-3 Advance | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | L2 | Pending | Yes | [5 empty] | Breaker is not compliant
232 | 1470 | Mandi Faizabad | Rented | Sheikhupura | Faisalabad | LESCO | Pantera | Cluster-2 | Completed | On-Grid | Eliminated |  |  | 10.26 | 10 |  |  |  |  | Elevated |  | Yes (site dropped) emailed to atiq for relocation 12-7-24 | [5 empty] | Breaker is not compliant
233 | 1610 | Lahore Road Sheikhupura | Rented | Sheikhupura | Faisalabad | LESCO | Pantera | Cluster-2 | Completed | On-Grid | Eliminated |  |  | 10.26 | 10 |  |  |  |  | Elevated |  | Yes (site dropped) emailed to atiq for relocation 12-7-24 | [5 empty] | Breaker is not compliant
234 | 392 | Behal | Rented | Mianwali | Sargodha | FESCO | Pantera | Cluster-2 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Pending | Yes | [5 empty] | Breaker is not compliant
235 | 427 | Garrote | Rented | Mianwali | Sargodha | FESCO | Pantera | Cluster-3 Advance | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Pending | Yes | [5 empty] | Breaker is not compliant
236 | 1668 | Behal Road Bhakkar | Rented | Mianwali | Sargodha | FESCO | Pantera | Cluster-2 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 18 | 0 | Elevated | Pending | Yes | [5 empty] | Breaker is not compliant
237 | 1331 | Lala Rukh | Rented | Fateh Jang | Islamabad | IESCO | REON | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 17.8435 | 0 | L2 | Completed | Yes | Yes | Yes | Yes | Received 25-Jul-24 | Solar Junction | Breaker is not compliant | In hand | 50% of invoice
238 | 668 | Injra | Rented | Fateh Jang | Islamabad | IESCO | REON | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 17.8435 | 0 | Elevated | Completed | Yes | Yes | Device Installed |  | Received 25-Jul-24 | Solar Junction | Breaker is not compliant | In hand | 40% of invoice
239 | 1248 | Pindi Gheb | Rented | Fateh Jang | Islamabad | IESCO | REON | Cluster-1 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
240 | 649 | Bahtar | Rented | Fateh Jang | Islamabad | IESCO | REON | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 17.8435 | 0 | Elevated | Completed | Yes | Yes | Yes | Yes | Received 25-Jul-24 | Solar Junction | Breaker is not compliant | In hand | 40% of invoice
241 | 475 | Nara | Rented | Fateh Jang | Islamabad | IESCO | REON | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 17.8435 | 0 | Elevated | Completed | Yes | Yes | Device Installed | Yes | Received 25-Jul-24 | Solar Junction | Breaker is not compliant | In hand | 40% of invoice
242 | 627 | Khunda | Rented | Fateh Jang | Islamabad | IESCO | REON | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 17.8435 | 0 | Elevated | Completed | Yes | Yes |  |  | Received 25-Jul-24 | Solar Junction | Breaker is not compliant | In hand | 40% of invoice
243 | 698 | Rawat | Owned | Rawalpindi Cantt | Islamabad | IESCO | REON | Cluster-1 | Completed | Hybrid | Feasible | Yes | Yes | 10.26 |  | 1 | 0 | 17.8435 | 1 | Elevated | Completed | Hybrid | Yes |  |  | Received 06-08-2024 | Al-Fateh | Breaker is not compliant
244 | 1687 | PWD | Owned | Rawalpindi Cantt | Islamabad | IESCO | REON | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 20 |  |  | 17.8435 | 0 | L3 + Elevated | Completed | Yes | Yes | Yes |  | Received 28-6-24 | Solar Junction | Breaker is not compliant | In hand | 40% of invoice
245 | 619 | Lalkurti | Owned | Rawalpindi Cantt | Islamabad | IESCO | REON | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 17.8435 | 0 | Elevated | Completed | Yes | Yes | Yes |  | Received 28-6-24 | Solar Junction | Breaker is not compliant | In hand | 40% of invoice
246 | 1115 | BRANCH DHOKE CHIRAGH DIN | Owned | RAWALPINDI CANTT | Rawalpindi | IESCO | REON | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 17.8435 | 0 | Elevated | Completed | Yes | Yes | Yes | Yes | Received 28-6-24 | Solar Junction | Breaker is not compliant | In hand | 50% of invoice
247 | 581 | Rawalpindi City Bank Square | Owned | Rawalpindi City | Islamabad | IESCO | REON | Cluster-1 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
248 | 633 | Satellite Town Rawalpindi | Owned | Rawalpindi City | Islamabad | IESCO | REON | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 17.8435 | 0 | Elevated | In Process | Yes | Commissioning in Process |  |  | Received 28-6-24 | Solar Junction | Breaker is not compliant | In hand | 40% of invoice
249 | 1012 | Pir Vadhai Rawalpindi | Owned | Rawalpindi City | Islamabad | IESCO | REON | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 20 |  |  | 17.8435 | 0 | Elevated | Completed | Yes | Yes | Yes | Yes | Completed & Paid | Solar Junction | Breaker is not compliant | In hand | 50% of invoice
250 | 614 | Jinnah Road Rawalpindi | Owned | Rawalpindi City | Islamabad | IESCO | REON | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 17.8435 | 0 | Elevated | Completed | Yes | Yes | Yes |  | Received 28-6-24 | Solar Junction | Breaker is not compliant | In hand | 40% of invoice
251 | 361 | Tank Adda D.I. Khan | Owned | Kohat | Peshawar | PESCO | REON | Cluster-2 | Completed | Hybrid | Feasible | Yes | Yes | 10.26 |  | 1 | 1 | 17.8435 | 2 | Elevated | Completed | Hybrid | Yes | Device Installed |  | Received 06-08-2024 | Al-Fateh | Breaker is not compliant
252 | 291 | Bannu City | Owned | Kohat | Peshawar | PESCO | REON | Cluster-2 | Completed | Hybrid | Feasible | Yes | Yes | 10.26 |  | 1 | 0 | 17.8435 | 2 | Elevated | Completed | Hybrid | Yes | Yes |  | Received 06-08-2024 | Al-Fateh | Breaker is not compliant
253 | 1502 | Parhoti Mardan | Owned | Mardan | Peshawar | PESCO | REON | Cluster-1 | Completed | Hybrid | Feasible | Yes | Yes | 10.26 |  | 1 | 0 | 17.8435 | 1 | Elevated | Completed | Hybrid | Yes | Device Installed |  | Received 25-Jul-24 | Solar Junction | Breaker is not compliant | In hand | 40% of invoice
254 | 866 | Pir Baba | Rented | Mardan | Peshawar | PESCO | REON | Cluster-1 | Completed | Hybrid | Feasible | Yes | Yes | 10.26 |  | 1 | 0 | 17.8435 | 2 | L3 + Elevated | Completed | Hybrid | Yes |  |  | Received 06-08-2024 | Al-Fateh | Breaker is not compliant
255 | 310 | Main Bazar, Takht Bhai | Rented | Mardan | Peshawar | PESCO | REON | Cluster-1 | Completed | Hybrid | Feasible | Yes | Yes | 10.26 |  | 1 | 0 | 17.8435 | 2 | Elevated | Completed | Hybrid | Yes | Device Installed | Yes | Received 25-Jul-24 | Solar Junction | Breaker is not compliant | In hand | 40% of invoice
256 | 1088 | Pabbi | Owned | Peshawar East | Peshawar | PESCO | REON | Cluster-1 | Completed | Hybrid | Feasible | Yes | Yes | 10.26 |  | 1 | 0 | 17.8435 | 2 | Elevated | Completed | Hybrid | Yes | Device Installed |  | Received 25-Jul-24 | Solar Junction | Breaker is not compliant | In hand | 40% of invoice
257 | 1678 | Dalazak Road, Peshawar | Owned | Peshawar East | Peshawar | PESCO | REON | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 17.8435 | 0 | L2 + L3 + Elevated | Completed | Yes | Yes | Yes |  | Received 25-Jul-24 | Solar Junction | Breaker is not compliant | In hand | 40% of invoice
258 | 962 | Kohat Road Peshawar | Owned | Peshawar East | Peshawar | PESCO | REON | Cluster-1 | Completed | Hybrid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
259 | 292 | Tangi | Owned | Peshawar East | Peshawar | PESCO | REON | Cluster-1 | Completed | Hybrid | Feasible | Yes | Yes | 10.26 |  | 1 | 0 | 17.8435 | 1 | Elevated | Completed | Hybrid | Yes | Device Installed |  | Received 25-Jul-24 | Solar Junction | Breaker is not compliant | In hand | 40% of invoice
260 | 277 | Peshawar Cantt | Owned | Peshawar West | Peshawar | PESCO | REON | Cluster-1 | Completed | Hybrid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
261 | 1765 | Achini Payan Peshawar | Owned | Peshawar West | Peshawar | PESCO | REON | Cluster-1 | Completed | Hybrid | Feasible | Yes | Yes | 10.26 |  | 1 | 0 | 17.8435 | 2 | Elevated | Completed | Hybrid | Yes | Device Installed |  | Received 25-Jul-24 | Solar Junction | Breaker is not compliant | In hand | 40% of invoice
262 | 862 | Sunehri Masjid Road Peshawar Cantt | Owned | Peshawar West | Peshawar | PESCO | REON | Cluster-1 | Completed | Hybrid | Feasible | Yes | Yes | 10.26 |  | 1 | 0 | 17.8435 | 2 | Elevated | Completed | Hybrid | Yes | Yes |  | Received 25-Jul-24 | Solar Junction | Breaker is not compliant | In hand | 40% of invoice
263 | 276 | Chowk Yadgar Peshawar | Owned | Peshawar West | Peshawar | PESCO | REON | Cluster-1 | Completed | Hybrid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
264 | 585 | Abbottabad Main | Owned | Abbottabad | Abbottabad | PESCO | REON | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 25 |  |  | 17.8435 | 0 | Elevated | Completed | Yes | Yes | Yes |  | Received 06-08-2024 | Al-Fateh | Breaker is not compliant
265 | 1185 | Kamra Cantt. | Owned | Attock | Abbottabad | IESCO | REON | Cluster-2 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 17.8435 | 0 | Elevated | Completed | Yes | Yes |  |  | Received 06-08-2024 | Al-Fateh | Breaker is not compliant
266 | 745 | DANDA SHAH BELAWAL | Owned | Chakwal | Jhelum | IESCO | REON | Cluster-2 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 17.8435 | 0 | L3 + Elevated | Completed | Yes | Yes | Device Installed | Yes | Received 06-08-2024 | Al-Fateh | Breaker is not compliant
267 | 25 | Marriot Road Karachi | Owned | Karachi Central | Karachi West | KESC | REON | Cluster-3 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 17.8435 | 0 | Elevated | Completed | Yes (re-allocated) | Yes | Device Installed |  | Ordered 08-Aug-2024 | Solar Junction | Breaker is not compliant
268 | 1455 | Hawksbay Road Karachi | Owned | Karachi Central | Karachi West | KESC | REON | Cluster-3 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 17.8435 | 0 | Elevated | Completed | Yes (re-allocated) | Yes | Yes |  | Received 06-08-2024 | Al-Fateh | Breaker is not compliant
269 | 1515 | Safoora Goth Karachi | Owned | Karachi City | Karachi City | KESC | REON | Cluster-2 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
270 | 1456 | New Sabzi Mandi, Super Highway Karachi | Owned | Karachi City | Karachi City | KESC | REON | Cluster-2 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
271 | 75 | Hassan Square Karachi | Owned | Karachi City | Karachi City | KESC | REON | Cluster-3 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 20 |  |  | 17.8435 | 0 | Elevated | Completed | Yes (re-allocated) | Yes | Yes |  | Received 06-08-2024 | Al-Fateh | Breaker is not compliant
272 | 1345 | North Karachi Industrial Area | Owned | Karachi City | Karachi City | KESC | REON | Cluster-4 | Completed | On-Grid | Eliminated |  |  | 10.26 | 15 |  |  | 17.8435 | 0 |  |  | Yes - To be Returned to IT Warehouse | [5 empty] | Breaker is not compliant
273 | 1422 | Mehdi Towers Karachi | Owned | Karachi East | Karachi East | KESC | REON | Cluster-2 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 17.8435 | 0 | Elevated | Completed | Yes | Yes | Yes |  | Received 06-08-2024 | Al-Fateh | Breaker is not compliant
274 | 14 | Tariq Road Karachi | Owned | Karachi East | Karachi East | KESC | REON | Cluster-3 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 20 |  |  | 17.8435 | 0 | Elevated | Completed | Yes (re-allocated) | Yes |  |  | Received 06-08-2024 | Al-Fateh | Breaker is not compliant
275 | 1036 | Shah Faisal Colony No.3 Karachi | Owned | Karachi East | Karachi East | KESC | REON | Cluster-4 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 17.8435 | 0 | Elevated + L1 | Completed | Yes | Yes | Device Installed |  | Ordered 08-Aug-2024 | Solar Junction | Breaker is not compliant
276 | 982 | Saudabad Karachi | Owned | Karachi East | Karachi East | KESC | REON | Cluster-4 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
277 | 50 | Shah Faisal Colony No.1 Karachi | Owned | Karachi East | Karachi East | KESC | REON | Cluster-4 | Completed | Hybrid | Feasible | Yes | Yes | 10.26 |  | 1 | 0 | 17.8435 | 1 | Elevated | In Process | Hybrid | [5 empty] | Breaker is not compliant
278 | 1271 | KIA Branch | Owned | Karachi South | Karachi East | KESC | REON | Cluster-2 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 25 |  |  | 17.8435 | 0 | Elevated | Completed | Yes | Yes | Yes |  | Received 06-08-2024 | Al-Fateh | Breaker is not compliant
279 | 61 | Defence Housing Authority Karachi | Owned | Karachi South | Karachi East | KESC | REON | Cluster-3 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
280 | 11 | Mithadar Karachi | Owned | Karachi West | Karachi West | KESC | REON | Cluster-3 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
281 | 596 | Mirpur A.K Main | Owned | Mirpur A.K. | Jhelum | AJKED | REON | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 25 |  |  | 17.8435 | 0 | L3 | Completed | Yes | Yes | Yes |  | Received 08-08-2024 | Solar Junction | Breaker is not compliant | In hand | 40% of invoice
282 | 1341 | Mirpur Sector F-1 | Owned | Mirpur A.K. | Jhelum | AJKED | REON | Cluster-2 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
283 | 1669 | Bhimber A.K | Owned | Mirpur A.K. | Jhelum | AJKED | REON | Cluster-1 | Completed | On-Grid | Eliminated |  |  | 10.26 | 10 |  |  |  |  | Elevated |  | Yes (site dropped) emailed to atiq for relocation 12-7-24 | [5 empty] | Breaker is not compliant
284 | 1504 | Chatter Domel | Owned | Muzaffarabad A.K. | Abbottabad | AJKED | REON | Cluster-2 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 17.8435 | 0 | Elevated | Completed | Yes | Yes |  |  | Received 06-08-2024 | Al-Fateh | Breaker is not compliant
285 | 743 | Aliot | Rented | Muzaffarabad A.K. | Abbottabad | IESCO | REON | Cluster-2 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 17.8435 | 0 | Elevated | Completed | Yes | Yes |  |  | Received 06-08-2024 | Al-Fateh | Breaker is not compliant
286 | 874 | Osia | Rented | Muzaffarabad A.K. | Abbottabad | IESCO | REON | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 17.8435 | 0 | Elevated | Completed | Yes | Yes |  |  | Received 25-Jul-24 | Solar Junction | Breaker is not compliant | In hand | 40% of invoice
287 | 1421 | Up More North Karachi | Owned | Karachi City | Karachi City | KESC | REON | Cluster-2 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 50 |  |  | 17.8435 | 0 | Elevated | Completed | Yes | Yes | Device Installed |  | Ordered 08-Aug-2024 | Solar Junction | Breaker is not compliant
288 | 570 | Jinnah Road | Owned | Quetta | Quetta | QESCO | REON | Cluster-3 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
289 | 103 | Gambat | Owned | Sukkur | Sukkur | SEPCO | REON | Cluster-2 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 17.8435 | 0 | Elevated | Completed | Yes | Yes | Device Installed |  | Received 06-08-2024 | Al-Fateh | Breaker is not compliant
290 | 1696 | Tando Ghulam Ali | Rented | Badin | Hyderabad | HESCO | REON | Cluster-3 | Completed | Hybrid | Feasible | Yes | Yes | 10.26 |  | 1 | 1 | 17.8435 | 3 | Elevated | In Process | Hybrid | [5 empty] | Breaker is not compliant
291 | 80 | Gari Khata Hyderabad | Owned | Hyderabad | Hyderabad | HESCO | REON | Cluster-3 | Completed | Hybrid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
292 | 76 | Risala Road Hyderabad | Owned | Hyderabad | Hyderabad | HESCO | REON | Cluster-3 | Completed | Hybrid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
293 | 77 | Market Chowk Hyderabad | Owned | Hyderabad | Hyderabad | HESCO | REON | Cluster-3 | Completed | Hybrid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
294 | 84 | Anaj Mandi Larkana | Owned | Larkana | Sukkur | SEPCO | REON | Cluster-2 | Completed | Hybrid | Feasible | Yes | Yes | 10.26 |  | 2 | 0 | 17.8435 | 4 | Elevated | Completed | Hybrid | Yes |  |  | Received 06-08-2024 | Al-Fateh | Breaker is not compliant
295 | 971 | Main Road Khairpur Nathan Shah | Owned | Larkana | Sukkur | SEPCO | REON | Cluster-2 | Completed | Hybrid | Feasible | Yes | Yes | 10.26 |  | 1 | 0 | 17.8435 | 1 | Elevated | Completed | Hybrid | Yes |  |  | Received 06-08-2024 | Al-Fateh | Breaker is not compliant
296 | 1480 | Naseerabad | Owned | Larkana | Sukkur | SEPCO | REON | Cluster-2 | Completed | Hybrid | Feasible | Yes | Yes | 10.26 |  | 1 | 0 | 17.8435 | 3 | Elevated | Completed | Hybrid | Yes |  |  | Received 06-08-2024 | Al-Fateh | Breaker is not compliant
297 | 1877 | Chowki Samahni A.K | Rented | Mirpur A.K. | Jhelum | AJKED | REON | Cluster-2 | Completed | Hybrid | Feasible | Yes | Yes | 10.26 |  | 0 | 1 | 17.8435 | 1 | Elevated | Completed | Hybrid | Yes |  |  | Received 06-08-2024 | Al-Fateh | Breaker is not compliant
298 | 1754 | Sangot A.K | Owned | Mirpur A.K. | Jhelum | AJKED | REON | Cluster-3 | Completed | Hybrid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
299 | 1894 | Rajdhani A.K | Rented | Mirpur A.K. | Jhelum | AJKED | REON | Cluster-2 | Completed | Hybrid | Feasible | Yes | Yes | 10.26 |  | 0 | 1 | 17.8435 | 1 | Elevated | Completed | Hybrid | Yes |  |  | Received 06-08-2024 | Al-Fateh | Breaker is not compliant
300 | 812 | Sir Syed Road Mirpurkhas | Owned | Mirpurkhas | Hyderabad | HESCO | REON | Cluster-3 | Completed | Hybrid | Feasible | Yes | Yes | 10.26 |  | 1 | 0 | 17.8435 | 1 | Elevated | Completed | Hybrid | Yes | Device Installed |  | Ordered 08-Aug-2024 | Solar Junction | Breaker is not compliant
301 | 94 | Tando Allahyar | Owned | Mirpurkhas | Hyderabad | HESCO | REON | Cluster-3 | Completed | Hybrid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
302 | 1775 | Tando Jan Muhammad | Rented | Mirpurkhas | Hyderabad | HESCO | REON | Cluster-3 | Completed | Hybrid | Feasible | Yes | Yes | 10.26 |  | 1 | 0 | 17.8435 | 3 | Elevated | Completed | Hybrid | Yes |  |  | Received 01-Aug-2024 | Al-Fateh | Breaker is not compliant
303 | 85 | Grain Market Mirpurkhas | Owned | Mirpurkhas | Hyderabad | HESCO | REON | Cluster-3 | Completed | Hybrid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
304 | 593 | Muzaffarabad AK | Owned | Muzaffarabad A.K. | Abbottabad | AJKED | REON | Cluster-2 | Completed | Hybrid | Feasible | Yes | Yes | 10.26 |  | 1 | 0 | 17.8435 | 1 | Elevated | Completed | Hybrid | Yes |  |  | Received 06-08-2024 | Al-Fateh | Breaker is not compliant
305 | 1595 | Sehnsa AK | Rented | Muzaffarabad A.K. | Abbottabad | AJKED | REON | Cluster-2 | Completed | Hybrid | Feasible | Yes | Yes | 10.26 |  | 1 | 0 | 17.8435 | 1 | Elevated | In Process | Hybrid | [5 empty] | Breaker is not compliant
306 | 714 | Rawalakot AK | Rented | Muzaffarabad A.K. | Abbottabad | AJKED | REON | Cluster-3 | Completed | Hybrid | Feasible | Yes | Yes | 10.26 |  | 1 | 0 | 17.8435 | 1 | Elevated | Completed | Hybrid | Yes |  |  | Received 06-08-2024 | Al-Fateh | Breaker is not compliant
307 | 4014 | Pang Peeran | Rented | Muzaffarabad A.K. | Abbottabad | AJKED | REON | Cluster-3 | Completed | Hybrid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
308 | 1156 | Dammas AK | Rented | Muzaffarabad A.K. | Abbottabad | AJKED | REON | Cluster-2 | Completed | Hybrid | Feasible | Yes | Yes | 10.26 |  | 1 | 0 | 17.8435 | 1 | L2 | In Process | Hybrid | [5 empty] | Breaker is not compliant
309 | 1625 | Dhirkot | Rented | Muzaffarabad A.K. | Abbottabad | AJKED | REON | Cluster-3 | Completed | Hybrid | Feasible | Yes | Yes | 10.26 |  | 1 | 0 | 17.8435 | 1 | Elevated | In Process | Hybrid | [5 empty] | Breaker is not compliant
310 | 1616 | Hattian Bala AK | Rented | Muzaffarabad A.K. | Abbottabad | AJKED | REON | Cluster-3 | Completed | Hybrid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
311 | 1624 | Balooch AK | Rented | Muzaffarabad A.K. | Abbottabad | AJKED | REON | Cluster-3 | Completed | Hybrid | Feasible | Yes | Yes | 10.26 |  | 0 | 1 | 17.8435 | 1 | Elevated | Completed | Hybrid | Yes |  |  | Ordered 08-Aug-2024 | Al-Fateh | Breaker is not compliant
312 | 1332 | Pulahir | Rented | Muzaffarabad A.K. | Abbottabad | AJKED | REON | Cluster-2 | Completed | Hybrid | Feasible | Yes | Yes | 10.26 |  | 1 | 0 | 17.8435 | 2 | Elevated | In Process | Hybrid | [5 empty] | Breaker is not compliant
313 | 1670 | Pallandri | Rented | Muzaffarabad A.K. | Abbottabad | AJKED | REON | Cluster-3 | Completed | Hybrid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
314 | 1627 | Seeta Road | Rented | Naushero Feroze | Sukkur | SEPCO | REON | Cluster-2 | Completed | Hybrid | Feasible | Yes | Yes | 10.26 |  | 1 | 0 | 17.8435 | 2 | Elevated | Completed | Hybrid | Yes |  |  | Received 06-08-2024 | Al-Fateh | Breaker is not compliant
315 | 788 | Sobho Dero | Rented | Naushero Feroze | Sukkur | SEPCO | REON | Cluster-3 | Completed | Hybrid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
316 | 102 | Mehrabpur | Owned | Naushero Feroze | Sukkur | SEPCO | REON | Cluster-3 | Completed | Hybrid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
317 | 97 | Sanghar | Rented | Nawabshah | Hyderabad | HESCO | REON | Cluster-3 | Completed | Hybrid | Feasible | Yes | Yes | 10.26 |  | 2 | 0 | 17.8435 | 4 | Elevated | Completed | Hybrid | Yes |  |  | Received 01-Aug-2024 | Al-Fateh | Breaker is not compliant
318 | 1859 | Kazi Ahmed | Rented | Nawabshah | Hyderabad | HESCO | REON | Cluster-2 | Completed | Hybrid | Feasible | Yes | Yes | 10.26 |  | 2 | 0 | 17.8435 | 4 | Elevated | In Process | Hybrid | Commissioning in Process |  |  | Ordered 08-Aug-2024 | Solar Junction | Breaker is not compliant
319 | 118 | Oderolal Station | Rented | Nawabshah | Hyderabad | HESCO | REON | Cluster-3 | Completed | Hybrid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
320 | 90 | Shahdadpur | Owned | Nawabshah | Hyderabad | HESCO | REON | Cluster-3 | Completed | Hybrid | Feasible | Yes | Yes | 10.26 |  | 1 | 0 | 17.8435 | 1 |  | Completed | Hybrid | Yes |  |  | Ordered 08-Aug-2024 | Solar Junction | Breaker is not compliant
321 | 96 | Daur | Rented | Nawabshah | Hyderabad | HESCO | REON | Cluster-3 | Completed | Hybrid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
322 | 1466 | S. Mandi Hazar Ganji Quetta | Owned | Quetta | Quetta | QESCO | REON | Cluster-3 | Completed | Hybrid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
323 | 5019 | Circle Office Quetta | Owned | Quetta | Quetta | QESCO | REON | Cluster-3 | Completed | Hybrid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
324 | 1288 | Meconghy Road | Owned | Quetta | Quetta | QESCO | REON | Cluster-2 | Completed | Hybrid | Feasible | Yes | Yes | 10.26 |  | 1 | 0 | 17.8435 | 1 | Elevated | In Process | Hybrid | [5 empty] | Breaker is not compliant
325 | 566 | Maizai Adda | Rented | Quetta | Quetta | QESCO | REON | Cluster-4 | Completed | Hybrid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
326 | 573 | Zarghoon Road | Owned | Quetta | Quetta | QESCO | REON | Cluster-3 | Completed | Hybrid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
327 | 1072 | Satellite Town | Owned | Quetta | Quetta | QESCO | REON | Cluster-2 | Completed | Hybrid | Feasible | Yes | Yes | 10.26 |  | 2 | 0 | 17.8435 | 2 |  | In Process | Hybrid | [5 empty] | Breaker is not compliant
328 | 559 | Toghi Road | Owned | Quetta | Quetta | QESCO | REON | Cluster-3 | Completed | Hybrid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
329 | 88 | Marich Bazar Sukkur | Rented | Sukkur | Sukkur | SEPCO | REON | Cluster-3 | Completed | Hybrid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
330 | 126 | Ghotki Branch | Owned | Sukkur | Sukkur | SEPCO | REON | Cluster-3 | Completed | Hybrid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
331 | 317 | Alpurai | Owned | Swat | Abbottabad | PESCO | REON | Cluster-3 | Completed | Hybrid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
332 | 280 | Mingora Main | Owned | Swat | Abbottabad | PESCO | REON | Cluster-3 | Completed | Hybrid | Eliminated |  |  | 10.26 |  |  |  | 17.8435 |  | Elevated | [7 empty] | Breaker is not compliant
333 | 151 | Mingora Green Chowk | Rented | Swat | Abbottabad | PESCO | REON | Cluster-1 | Completed | Hybrid | Feasible | Yes | Yes | 10.26 |  | 1 | 0 | 17.8435 | 2 | Elevated | Completed | Hybrid | Yes | Device Installed |  | Received 06-08-2024 | Al-Fateh | Breaker is not compliant
334 | 288 | Dir | Owned | Swat | Abbottabad | PESCO | REON | Cluster-3 | Completed | Hybrid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
335 | 456 | Behrain | Owned | Swat | Abbottabad | PESCO | REON | Cluster-3 | Completed | Hybrid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
336 | 711 | Bisham | Rented | Swat | Abbottabad | PESCO | REON | Cluster-3 | Completed | Hybrid | Feasible | Yes | Yes | 10.26 |  | 1 | 0 | 17.8435 | 2 | Elevated | Completed | Hybrid | Yes | Device Installed |  | Ordered 08-Aug-2024 | Al-Fateh | Breaker is not compliant
337 | 59 | Pasni | Rented | Makran | Makran | QESCO | REON | Cluster-2 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
338 | 1487 | Jinnah Avenue | Rented | Makran | Makran | QESCO | REON | Cluster-3 | Completed | Hybrid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
339 | 1614 | Ormara | Rented | Makran | Makran | QESCO | REON | Cluster-3 | Completed | Hybrid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
340 | 8080 | Airport Road Gwadar | Rented | Makran | Makran | QESCO | REON | Cluster-2 | Completed | Hybrid | Feasible | Yes | Yes | 10.26 |  | 2 | 0 | 17.8435 | 2 | Elevated | Pending | No - shifted to 1611 | [5 empty] | Breaker is not compliant
341 | 3040 | Marine Drive Gwadar | Rented | Makran | Makran | QESCO | REON | Cluster-3 | Completed | Hybrid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
342 | 553 | SIBI | Rented | Khuzdar | Khuzdar | QESCO | REON | Cluster-3 | Completed | Hybrid | Feasible | Yes | Yes | 10.26 |  | 1 | 0 | 17.8435 | 3 | Elevated | In Process | Hybrid | [5 empty] | Breaker is not compliant
343 | 563 | MASTUNG | Rented | Khuzdar | Khuzdar | QESCO | REON | Cluster-3 | Completed | Hybrid | Feasible | Yes | Yes | 10.26 |  | 1 | 0 | 17.8435 | 1 | Elevated | In Process | Hybrid | [5 empty] | Breaker is not compliant
344 | 567 | KHUZDAR | Rented | Khuzdar | Khuzdar | QESCO | REON | Cluster-3 | Completed | Hybrid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
345 | 4048 | DHADAR | Rented | Khuzdar | Khuzdar | QESCO | REON | Cluster-4 | Completed | Hybrid | Eliminated |  |  | 10.26 | [5 empty] | Elevated |  | Hybrid | [5 empty] | Breaker is not compliant
346 | 4064 | SURAB | Rented | Khuzdar | Khuzdar | QESCO | REON | Cluster-3 | Completed | Hybrid | Eliminated |  |  | 10.26 | [5 empty] | Elevated |  | Hybrid | [5 empty] | Breaker is not compliant
347 | 1274 | Umerkot | Rented | Mirpurkhas | Hyderabad | HESCO | REON | Cluster-3 | Completed | Hybrid | Eliminated |  |  | 10.26 |  | 0 | 0 | 17.8435 | 0 | ELevated |  | Hybrid | [5 empty] | Breaker is not compliant
348 | 4010 | Tando Jam | Rented | Mirpurkhas | Hyderabad | HESCO | REON | Cluster-2 | Completed | Hybrid | Feasible | Yes | Yes | 10.26 |  | 1 | 0 | 17.8435 | 2 | Elevated | Completed | Hybrid | Yes |  |  | Received 06-08-2024 | Al-Fateh | Breaker is not compliant
349 | 8010 | Bori Bazar | Rented | Hyderabad | Hyderabad | HESCO | REON | Cluster-3 | Completed | Hybrid | Feasible | Yes | Yes | 10.26 |  | 1 | 1 | 17.8435 | 1 | Elevated | In Process | Hybrid | [5 empty] | Breaker is not compliant
350 | 1813 | Rachna Town | Rented | Lahore City | Lahore West | LESCO | Pantera | Cluster-3 Advance | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 20 |  |  | 18 | 0 | Elevated | Pending | Yes | [5 empty] | Breaker is not compliant
351 | 1843 | Quid e Azam interchange | Rented | Lahore City | Lahore West | LESCO | Pantera | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes |  | Received 11-Jul-2024 | Solar Junction | Breaker is not compliant | Deposit in CAD | 20% supplies - Approval CTs awaited
352 | 1701 | MCB Center Lahore | Owned | Lahore Defence | Lahore East | LESCO | Pantera | Pending |  | On-Grid |  |  |  | 10.26 | [13 empty] | Breaker is not compliant
353 | 8036 | Punjab Cooperative Society Branch | Rented | Lahore Defence | Lahore East | LESCO | Pantera | Cluster-2 | Completed | On-Grid | Eliminated |  |  | 10.26 | [7 empty] | No - shifted to 1455 | [5 empty] | Breaker is not compliant
354 | 218 | Liberty Market Lahore | Rented | Lahore Gulberg | Lahore East | LESCO | PANTERA | Cluster-3 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
355 | 4002 | Central Park Lahore | Rented | Lahore Gulberg | Lahore East | LESCO | Pantera | Cluster-3 | Completed | On-Grid | Eliminated |  |  | 10.26 | 10 |  |  | 18 | 0 | Elevated |  | Yes (site dropped) emailed to Mohsin Irshad 19-7-24 | [5 empty] | Breaker is not compliant
356 | 727 | Illaqa Nawab Sahib | Owned | Lahore Johar Town | Lahore East | LESCO | Pantera | Cluster-3 | Completed | On-Grid | Eliminated |  |  | 10.26 | [5 empty] | Elevated | [7 empty] | Breaker is not compliant
357 | 1899 | Chung Branch Lahore | Rented | Lahore Multan Road | Lahore West | LESCO | Pantera | Pending |  | On-Grid |  |  |  | 10.26 | [13 empty] | Breaker is not compliant
358 | 1226 | Jaddah Branch | Rented | Lahore City | Lahore West | LESCO | PANTERA | Cluster-1 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Completed | Yes | Yes | Yes |  | Received 25-6-24 | Solar Junction | Breaker is not compliant | Deposit in CAD | 20% supplies - Approval CTs awaited
359 | 551 | Shahra-e-Iqbal Quetta | Owned | Quetta | Karachi | QESCO | REON | Cluster-4 | Completed | Hybrid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
360 | 564 | Zhob | Rented | Quetta | Karachi | QESCO | REON | Cluster-4 | Completed | Hybrid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
361 | 1574 | Muslim Bagh | Rented | Quetta | Karachi | QESCO | REON | Cluster-4 | Completed | Hybrid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
362 | 112 | Chak | Rented | Sukkur | Hyderabad | SEPCO | REON | Cluster-3 | Completed | Hybrid | Eliminated |  |  | 10.26 |  |  |  | 17.8435 |  | Elevated |  | Hybrid | [5 empty] | Breaker is not compliant
363 | 123 | Kambar Ali Khan | Rented | Sukkur | Hyderabad | SEPCO | REON | Cluster-3 | Completed | Hybrid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
364 | 144 | Kumb | Rented | Sukkur | Hyderabad | SEPCO | REON | Cluster-3 | Completed | Hybrid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
365 | 742 | Phulji Station | Rented | Sukkur | Hyderabad | SEPCO | REON | Cluster-3 | Completed | Hybrid | Feasible | Yes | Yes | 10.26 |  | 1 | 0 | 17.8435 | 1 | Elevated | Completed | Hybrid | Yes |  |  | Received 06-08-2024 | Al-Fateh | Breaker is not compliant
366 | 838 | Phull Village | Rented | Sukkur | Hyderabad | SEPCO | REON | Cluster-3 | Completed | Hybrid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
367 | 898 | Pir Jo Goth | Rented | Sukkur | Hyderabad | SEPCO | REON | Cluster-3 | Completed | Hybrid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
368 | 1173 | Adda Mureed Shakh | Rented | Sukkur | Hyderabad | SEPCO | REON | Cluster-3 | Completed | Hybrid | Eliminated |  |  | 10.26 |  |  |  | 17.8435 |  | Elevated |  | Hybrid | [5 empty] | Breaker is not compliant
369 | 1359 | Agha Qadirdad Market Sukkur | Rented | Sukkur | Hyderabad | SEPCO | REON | Cluster-3 | Completed | Hybrid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
370 | 1467 | Main Chowk Saleh Pat | Rented | Sukkur | Hyderabad | SEPCO | REON | Cluster-3 | Completed | Hybrid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
371 | 1662 | Akri Chowdagi | Rented | Sukkur | Hyderabad | SEPCO | REON | Cluster-3 | Completed | Hybrid | Eliminated |  |  | 10.26 |  |  |  | 17.8435 |  | Elevated |  | Hybrid | [5 empty] | Breaker is not compliant
372 | 1683 | Mero Khan | Rented | Sukkur | Hyderabad | SEPCO | REON | Cluster-4 | Completed | Hybrid | Eliminated |  |  | 10.26 |  |  |  | 17.8435 |  | Elevated |  | Hybrid | [5 empty] | Breaker is not compliant
373 | 1886 | Lalu Ranuk | Rented | Sukkur | Hyderabad | SEPCO | REON | Cluster-3 | Completed | Hybrid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
374 | 1825 | Shamsi Road Mardan | Rented | Peshawar | Peshawar | PESCO | REON | Cluster-4 | Completed | Hybrid | Eliminated |  |  | 10.26 |  |  |  | 17.8435 |  | Elevated |  | Hybrid | [5 empty] | Breaker is not compliant
375 | 1681 | Shah Mansoor | Rented | Peshawar | Peshawar | PESCO | REON | Cluster-4 | Completed | Hybrid | Feasible | Yes | Yes | 10.26 |  | 1 | 0 | 17.8435 | 1 | Elevated | Completed | Hybrid | Yes |  |  | Received 06-08-2024 | Al-Fateh | Breaker is not compliant
376 | 315 | Lund Khawar | Rented | Peshawar | Peshawar | PESCO | REON | Cluster-3 | Completed | Hybrid | Feasible | Yes | Yes | 10.26 |  | 1 | 1 | 17.8435 | 2 | Elevated | Completed | Hybrid | Yes |  |  | Received 06-08-2024 | Al-Fateh | Breaker is not compliant
377 | 4041 | Sowari | Rented | Peshawar | Peshawar | PESCO | REON | Cluster-4 | Completed | Hybrid | Feasible | Yes | Yes | 10.26 |  | 1 | 0 | 17.8435 | 1 | Elevated | Completed | Hybrid | Yes |  |  | Received 06-08-2024 | Al-Fateh | Breaker is not compliant
378 | 664 | Village Lehri |  | Jhelum | Islamabad | IESCO | BEL | Cluster-4 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
379 | 933 | Civil Lines Jhelum |  | Jhelum | Islamabad | IESCO | BEL | Cluster-4 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 18 | 0 | Elevated | Pending | To be Issued | [5 empty] | Breaker is not compliant
380 | 4059 | Mandra |  | Jhelum | Islamabad | IESCO | BEL | Cluster-4 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Pending | To be Issued | [5 empty] | Breaker is not compliant
381 | 4061 | Sanghoi |  | Jhelum | Islamabad | IESCO | BEL | Cluster-4 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Pending | To be Issued | [5 empty] | Breaker is not compliant
382 | 1719 | Mangla Road Dina |  | Mirpur A.K. | Islamabad | IESCO | BEL | Cluster-4 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
383 | 4003 | Kot Jamel A.K. | Rental | Jhelum | Islamabad | AJKED | REON | Cluster-4 | Completed | Hybrid | Eliminated |  |  | 10.26 |  |  |  | 17.8435 |  | Elevated |  | Hybrid | [5 empty] | Breaker is not compliant
384 | 1505 | Main Bazar Chakswari A.K. | Rented | Jhelum | Islamabad | AJKED | REON | Cluster-3 | Completed | Hybrid | Feasible | Yes | Yes | 10.26 |  | 1 | 0 | 17.8435 | 1 | Elevated | Completed | Hybrid | Yes |  |  | Ordered 08-Aug-2024 | Al-Fateh | Breaker is not compliant
385 | 4 | Saddar Karachi | Owned | Karachi East | Karachi | KESC | REON | Cluster-3 | Completed | Hybrid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
386 | 92 | Saeedabad | Rental | Hyderabad | Hyderabad | HESCO | REON | Cluster-4 | Completed | Hybrid | Eliminated |  |  | 10.26 |  |  |  | 17.8435 |  | Elevated |  | Hybrid | [5 empty] | Breaker is not compliant
387 | 93 | Naukot | Rental | Hyderabad | Hyderabad | HESCO | REON | Cluster-3 | Completed | Hybrid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
388 | 107 | Tando Mohammed Khan | Rental | Hyderabad | Hyderabad | HESCO | REON | Cluster-4 | Completed | Hybrid | Feasible | Yes | Yes | 10.26 |  | 1 | 0 | 17.8435 | 1 | Elevated | Completed | Hybrid | Yes |  |  | Received 01-Aug-2024 | Al-Fateh | Breaker is not compliant
389 | 150 | Thatta | Rental | Hyderabad | Hyderabad | HESCO | REON | Cluster-4 | Completed | Hybrid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
390 | 875 | Badin | Rental | Hyderabad | Hyderabad | HESCO | REON | Cluster-4 | Completed | Hybrid | Feasible | Yes | Yes | 10.26 |  | 1 | 0 | 17.8435 | 1 | Elevated | In Process | Hybrid | Commissioning in Process |  |  | Ordered 08-Aug-2024 | Solar Junction | Breaker is not compliant
391 | 925 | Jhudo | Rental | Hyderabad | Hyderabad | HESCO | REON | Cluster-4 | Completed | Hybrid | Eliminated |  |  | 10.26 |  | 0 | 0 | 17.8435 | 0 | Elevated |  | Hybrid | [5 empty] | Breaker is not compliant
392 | 1252 | Matli | Rental | Hyderabad | Hyderabad | HESCO | REON | Cluster-4 | Completed | Hybrid | Eliminated |  |  | 10.26 |  |  | 0 | 17.8435 |  | Elevated | [7 empty] | Breaker is not compliant
393 | 1499 | Jamrao Road, Sanghar | Rental | Hyderabad | Hyderabad | HESCO | REON | Cluster-4 | Completed | Hybrid | Feasible | Yes | Yes | 10.26 |  | 2 | 0 | 17.8435 | 1 | Elevated | Completed | Hybrid | Yes |  |  | Received 01-Aug-2024 | Al-Fateh | Breaker is not compliant
394 | 1675 | Mithi | Rental | Hyderabad | Hyderabad | HESCO | REON | Cluster-4 | Completed | Hybrid | Feasible | Yes | Yes | 10.26 |  | 1 | 1 | 17.8435 | 1 | L3 | In Process | Hybrid | Commissioning in Process |  |  | Ordered 08-Aug-2024 | Solar Junction | Breaker is not compliant
395 | 1739 | Islamkot | Rental | Hyderabad | Hyderabad | HESCO | REON | Cluster-4 | Completed | Hybrid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
396 | 225 | Depalpur |  | Sahiwal | Multan | MEPCO | BEL | Cluster-4 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 18 | 0 | Elevated | Pending | To be Issued | [5 empty] | Breaker is not compliant
397 | 545 | Adda Zakheera Dunyapur | Rented | Bahawalpur | Multan | MEPCO | BEL | Cluster-4 | Completed | On-Grid | Eliminated |  |  | 10.26 |  |  |  | 18 | 0 | Elevated | [7 empty] | Breaker is not compliant
398 | 1731 | Dhanote |  | Bahawalpur | Multan | MEPCO | BEL | Cluster-4 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
399 | 679 | Chowk Sarwar Shaheed Rangpur |  | Multan | Multan | MEPCO | BEL | Cluster-4 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Pending | To be Issued | [5 empty] | Breaker is not compliant
400 | 154 | Sarishta Thall Layyah |  | Multan | Multan | MEPCO | BEL | Cluster-4 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Pending | To be Issued | [5 empty] | Breaker is not compliant
401 | 847 | Paigah |  | Multan | Multan | MEPCO | BEL | Cluster-4 | Completed | On-Grid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
402 | 961 | Delhi Gate Multan |  | Multan | Multan | MEPCO | BEL | Cluster-4 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 18 | 0 | Elevated | Pending | To be Issued | [5 empty] | Breaker is not compliant
403 | 819 | Adda Dijkot | Rented | Faisalabad | Faisalabad | FESCO | Pantera | Cluster-3 | Completed | On-Grid | Eliminated |  |  | 10.26 | [5 empty] | Elevated | [7 empty] | Breaker is not compliant
404 | 376 | Buchiana |  | Faisalabad | Faisalabad | FESCO | Pantera | Cluster-3 Advance | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Pending | To be Issued | [5 empty] | Breaker is not compliant
405 | 1524 | Samundari Road Faisalabad | Rented | Faisalabad | Faisalabad | FESCO | Pantera | Cluster-3 | Completed | On-Grid | Eliminated |  |  | 10.26 |  |  |  | 18 | 0 | Elevated | [7 empty] | Breaker is not compliant
406 | 4096 | Lalamusa Sabzi Mandi G. T. Road |  | Sialkot | Faisalabad | FESCO | Pantera | Cluster-3 Advance | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Pending | To be Issued | [5 empty] | Breaker is not compliant
407 | 458 | Ahmedpur Sial |  | Sialkot | Faisalabad | FESCO | Pantera | Cluster-3 Advance | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 15 |  |  | 18 | 0 | Elevated | Pending | To be Issued | [5 empty] | Breaker is not compliant
408 | 1229 | Mari Shah Sakhira |  | Sialkot | Faisalabad | FESCO | Pantera | Cluster-3 Advance | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Pending | To be Issued | [5 empty] | Breaker is not compliant
409 | 1490 | Adda Mahmood Kot |  | Sialkot | Faisalabad | FESCO | Pantera | Cluster-3 Advance | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Pending | To be Issued | [5 empty] | Breaker is not compliant
410 | 1617 | Bhone | Owned | Sialkot | Faisalabad | ShakarGanj Mills | Pantera | Cluster-3 | Completed | On-Grid | Eliminated |  |  | 10.26 | [5 empty] | Elevated | [7 empty] | Breaker is not compliant
411 | 1728 | Wahga |  | Lahore | Lahore | LESCO | Pantera | Cluster-3 Advance | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 18 | 0 | Elevated | Pending | To be Issued | [5 empty] | Breaker is not compliant
412 | 5009 | Cricle Office Faisalabad |  | Faisalabad | Faisalabad | FESCO | Pantera | Pending |  | On-Grid |  |  |  | 10.26 | [13 empty] | Breaker is not compliant
413 | 764 | Bedian Road Lahore | Rented | Lahore | Lahore | LESCO | REON | Cluster-4 | Completed | Hybrid | Feasible | Yes | Yes | 10.26 |  | 1 | 0 | 17.8435 | 1 | Elevated | Completed | Hybrid | Yes |  |  | Ordered 08-Aug-2024 | Al-Fateh | Breaker is not compliant
414 | 1789 | Karachi East |  | Karachi | Karachi | KESC | REON | Cluster-4 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 10 |  |  | 17.8435 | 0 | Elevated | In Process | Yes | [5 empty] | Breaker is not compliant
415 | 989 | Sukkur | Rental | Larkana | SUkkur | SEPCO | REON | Cluster-4 | Completed | Hybrid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
416 | 1764 | Peshawar | Rented | mardan | PEshawar | PESCO | REON | Cluster-4 | Completed | Hybrid | Feasible | Yes | Yes | 10.26 |  | 1 | 0 | 17.8435 | 1 | Elevated | Completed | Hybrid | Yes |  |  | Ordered 08-Aug-2024 | Al-Fateh | Breaker is not compliant
417 | 286 | Yar Hussain | Rental | Mardan | PEshawar | PESCO | REON | Cluster-4 | Completed | Hybrid | Eliminated |  |  | 10.26 | [13 empty] | Breaker is not compliant
418 | 279 | The Mall Mardan |  | Mardan | Peshawar | PESCO | REON | Cluster-4 | Completed | Hybrid | Feasible | Yes | Yes | 10.26 |  | 1 | 1 | 17.8435 | 2 | Elevated | Completed | Hybrid | Yes |  |  | Received 06-08-2024 | Al-Fateh | Breaker is not compliant
419 | 326 | MCB Circle Office Branch | Owned | Faisalabad | Faisalabad | FESCO | Pantera | Cluster-3 Advance | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 50 |  |  | 18 | 0 | Elevated | Pending | To be Issued | [5 empty] | Breaker is not compliant
420 | 8259 | MCB Aiwan-e-Tijarat China Chowk Lahore | Owned | Lahore | Lahore | LESCO | Pantera | Cluster-2 | Completed | On-Grid | Feasible | Yes | Yes | 10.26 | 115 | 0 | 0 | 18 | 0 | Elevated | Completed | Yes | Yes | Yes |  | Received 09-Jul-2024 | Al-Fateh | Breaker is not compliant | In hand 3-7-2024
421 | 1599 | Charsadda Road Mardan | Rented | mardan | Peshawar | PESCO | REON | Pending |  | Hybrid |  |  |  | 10.26 |  |  |  | 17.8435 |  | Elevated |  | Hybrid | [5 empty] | Breaker is not compliant
422 | 8030 | Hangu Road | [11 empty] | 10.26 | [13 empty] | Breaker is not compliant
423 | 1365 | Jandi Darsamand | [11 empty] | 10.26 | [13 empty] | Breaker is not compliant
424 | 1847 | Rangpur Adda | [11 empty] | 10.26 | [13 empty] | Breaker is not compliant
425 | 1637 | University Road | [11 empty] | 10.26 | [13 empty] | Breaker is not compliant
426 | 1732 | Karak | [11 empty] | 10.26 | [13 empty] | Breaker is not compliant
427 | 1878 | Zaida | Rented | Mardan |  |  | REON | Cluster-4 | Completed | Hybrid | Feasible | Yes | Yes | 10.26 |  | 1 | 0 | 17.8435 | 1 | Elevated | Pending | Hybrid | [5 empty] | Breaker is not compliant
428 | 1821 | AK Branch |  | AJK |  |  | REON | Cluster-4 | Completed | Hybrid | Feasible | Yes | Yes | 10.26 |  | 1 | 0 | 17.8435 | 1 | Elevated | Completed | Hybrid | Yes |  |  | Ordered 08-Aug-2024 | Al-Fateh | Breaker is not compliant

## Invoice Summary-Detail
PROJECT PAYMENT SUMMARY
SOLARIZATION PHASE-II PEC NO.6912 DATED 25-OCT-2023 | [8 empty] | APPROVED AMOUNT | [7 empty] | INVOICE AMOUNT
[9 empty] | US Dollars |  |  |  | PAK RUPEE |  |  |  | US Dollars |  |  |  | PAK RUPEE
S. No. | Vendor | Type | Invoice No. | Invoice Date | Equipment | Approved Rate Excl. GST (USD) | Approved Rate Excl. GST (PKR) | QTY. | Total Amount (USD) | GST % | GST Amount (USD) | Total Amount With GST (USD) | Total Amount (PKR) | GST % | GST Amount (PKR) | Total Amount with GST (PKR) | Total Amount (USD) | GST % | GST Amount (USD) | Total Amount With GST (USD) | Total Amount (PKR) | GST % | GST Amount (PKR) | Total Amount with GST (PKR) | Remarks | Status
1 | REON | Commercial Invoice | REL-MCB-CI-1-11/23 | 23.11.2023 | Panels per Watt | 1 | 0 | 1000000 | 1000000 | 0% | 0 | 1000000 |  |  | 0 | 0 | 200000 | 0% | 0 | 200000 | 10000000 |  | 0 |  | Commercial invoice 20% advance for panels | Paid 05-12-2023 bank advice
2 | REON | GST Invoice | 106441 | 2023-12-08 | Panels per Watt | 1 | 0 | 1000000 | 1000000 | 0% | 0 | 1000000 |  |  | 0 | 0 | 800000 | 0% | 0 | 800000 | 0 |  | 0 |  | GST invoice for 80% with GD Note for panels | 80% Amount paid 18-12-2023 bank advice GST invoice cleared
3 | REON | GST Invoice | 106423 | 2023-12-04 | Panels per Watt | 1 | 0 | 1000000 | 1000000 | 0% | 0 | 1000000 |  |  | 0 | 0 |  | 0% | 0 | 0 | 0 |  | 0 |  | GST invoice for 20% advance settlement of 37,800 USD | 20% Advance settled 18-12-2023 GST invoice cleared
4 | REON | Commercial Invoice | REL-MCB-CI-4-11/23 | 23.11.2023 | Inverters Hybrid | 0 | 10000 | 10 | 0 |  | 0 | 0 | 100000 | 10% | 10000 | 110000 |  | 10% |  | 0 | 100000 | 10% | 0 |  | Commercial Invoice 100% advance inverters excl. GST | Paid 30-11-2023 bank advice (GST to be Paid with final GST invoice)
5 | REON | Commercial Invoice | REL-MCB-CI-3-11/23 | 23.11.2023 | Batteries | 100 | 0 | 10 | 1000 | 18% | 180 | 1180 |  |  | 0 | 0 | 200 | 10% | 0 | 200 | 5000000 |  | 0 |  | Commercial Invoice 20% advance batteries excl. GST | Paid 05-12-2023 bank advice
6 | REON | GST Invoice | 106442 | 2023-12-08 | Batteries | 100 | 0 | 10 | 1000 | 18% | 180 | 1180 |  |  | 0 | 0 | 100 | 10% | 10 | 10 | 20000000 |  | 0 |  | GST invoice with 80% payment for batteries | 80% Amount paid 19-12-2023 bank advice with GST invoice cleared |  | SBP rate of invoice date 284.1439
7 | REON | GST Invoice | 106424 | 2023-12-04 | Batteries | 100 | 0 | 10 | 1000 | 18% | 180 | 1180 |  |  | 0 | 0 | 0 | 10% | 20 | 20 |  |  | 0 |  | GST invoice for payment of GST on 20% amount & settlement of advance 20352 USD | 20% Advance settled 19-12-2023 with payment of GST on 20% amount
8 | REON | Commercial Invoice | REL-MCB-CI-5-11/23 | 23.11.2023 | Local Supplies | 0 | 15000 | 10 | 0 | 18% | 0 | 0 | 150000 | 10% | 15000 | 165000 |  | 10% |  | 0 | 187500 | 10% | 0 |  | 50% advance excl. GST local supp. | Paid on 07-Feb-2024 Advice # 127406
9 | AE Solar | Sales Tax Invoice | 231137 | 15.11.2023 | Inverters On Grid 10kW | 1000 | 0 | 10 | 10000 | 18% | 1800 | 11800 | 2000000 | 10% | 200000 | 2200000 | 10000 | 10% | 1000 | 11000 | 2000000 | 10% | 200000 |  | Payment against 160 delivered stock | Paid 30-11-2023 bank advice
|  |  | 231137 |  | Inverters On Grid 20kW | 2000 | 0 | 10 | 20000 | 18% | 3600 | 23600 | 4000000 | 10% | 400000 | 4400000 | 20000 | 10% | 2000 | 22000 | 4000000 | 10% | 400000
10 | Pantera Energy | Commercial Invoice | 2084 | 17.11.2023 | Panels | 1 | 0 | 1000 | 1000 | 0% | 0 | 1000 |  |  | 0 | 0 | 200 | 0% | 0 | 200 | 1000000 |  | 0 |  | 20% advance panels excl. GST panels | Paid 30-11-2023 PO#109921279
11 | Pantera Energy | Commercial Invoice | 2085 | 11.12.2023 | Local Supplies |  |  | 10 | 0 | 0% | 0 | 0 |  |  | 0 | 0 | 0 | 0% | 0 | 0 | 1000000 |  | 0 |  | 80% advance excl. GST local supplies 30 branches | Paid 20-12-2023 PO#109921756 |  |  | supplies | 20523396
12 | BEL | Commercial Invoice | BEL-INV/2023/12/2577 | 18.12.023 | Panels | 1 |  | 1000 | 1000 | 0% | 0 | 1000 |  |  | 0 | 0 | 1000 | 0% | 0 | 1000 | 200000 |  | 0 |  | 100% payment (GST invoice) solar panel GD Note | Paid 15-01-2024 PO#109922416 |  |  | services | 6746000
13 | AE Solar | Sales Tax Invoice | 231240 | 21.12.2023 | Inverters On Grid 15kW | 3000 |  | 10 | 30000 | 0% | 5400 | 35400 | 6000000 |  | 1080000 | 7080000 | 30000 | 10% | 3000 | 33000 | 6000000 |  | 848358 |  | Payment against 40 delivered stock | Paid 15-01-2024 bank advice
|  |  | 231240 |  | Inverters On Grid 20kW | 2000 |  | 10 | 20000 | 0% | 3600 | 23600 | 4000000 |  | 720000 | 4720000 | 20000 | 10% | 2000 | 22000 | 4000000 |  | 565572
14 | Adamjee Insurance | Sales Tax Invoice |  |  | Insurance of inverters |  |  |  | 0 | 0% | 0 | 0 |  |  | 0 | 0 | 0 | 0% | 0 | 0 |  |  | 0 |  | Insurance cover for inverters in MCB IT Warehouse Lahore | Paid by CAD 05-01-2024 |  | 0
15 | Pantera Energy | Sales Tax Invoice | 2201 | 24.01.2024 | Panels | 1 | 0 | 10000 | 10000 | 0% | 0 | 10000 |  |  | 0 | 0 | 8000 | 0% | 0 | 10000 | 2000000 |  | 0 |  | 80% balance payment and settlement of 20% advance | Paid on 09-Feb-2024 PO# 109923142
16 | REON | Commercial Invoice | REL-MCB-CI-6-02/24 | 15.02.2024 | Local Supplies | 0 | 15000 | 10 | 0 | 18% | 0 | 0 | 150000 | 10% | 15000 | 165000 |  | 10% |  | 0 | 187500 | 10% | 0 |  | 50% advance excl. GST local supp. Cluster-2 | Paid
17 | Pantera Energy | Commercial Invoice |  |  | Local Supplies |  |  | 10 | 0 | 0% | 0 | 0 |  |  | 0 | 0 | 0 | 0% | 0 | 0 | 20000000 |  | 0 |  | 80% advance excl. GST (Cluster-2) - 30 Sites | Paid
18 | Pantera Energy | Commercial Invoice | 4099 | 2024-03-14 | Panels | 1 | 0 | 10000 | 10000 | 0% | 0 | 10000 |  |  | 0 | 0 | 2000 | 0% | 0 | 10000 | 10000000 |  | 0 |  | 20% advance panels excl. GST panels additional 700 panels | Paid 22-Mar-2024 PO#
19 | AE Solar | Sales Tax Invoice |  |  | Inverters On Grid 50kW | 5000 |  | 25 | 125000 | 0% | 22500 | 147500 | 25000000 |  | 4500000 | 29500000 | 125000 | 10% | 12500 | [5 empty] | Payment against 28 delivered stock | Paid 03-Apr-2024 bank advice
|  |  | 240226 | 2024-02-19 | Inverters On Grid 25kW | 4000
[5 empty] | Inverters On Grid 15kW | 3000 |  | 25 | 75000 | 0% | 13500 | 88500 | 15000000 |  | 2700000 | 17700000 | 75000 | 10% | 7500
20 | AE Solar | Amount Held
21 | Pantera Energy | Commercial Invoice | 2405 | 2024-04-05 | Panels | 1 | 0 | 10000 | 10000 | 0% | 0 | 10000 |  |  | 0 | 0 | 2000 | 0% | 0 | 5000 | 10000000 |  | 0 |  | 80% advance panels excl. GST panels additional 700 panels | Paid
22 | Solar Junction | Sales Tax Invoice | SJ/MCB/01-2024 |  | 16 | [19 empty] | Payment on visit and report submission | Paid 23-05-2024
25 | REON | Commercial Invoice | REL-MCB-CI-7-03/24 | 29.03.2024 | Local Supplies | 0 | 15000 | 10 | 0 | 18% | 0 | 0 | 150000 | 10% | 15000 | 165000 |  | 10% |  | 0 | 187500 | 10% | 0 |  | 50% advance excl. GST local supp. Cluster-3 | Paid
26 | BEL | Sales Tax Invoice | Various branches | 2024-02-28 | 35 completed branches | [19 empty] | 20% retain on hold after net metering | In Process
| BEL | Sales Tax Invoice | Various branches |  | 35 completed branches | [19 empty] | 80% paid on completion | Paid
27 | Pantera Energy | Sales Tax Invoice | Various branches | 2024-02-28 | 10 completed branches | [19 empty] | 100% amount incl. sales tax | In Process
27 | REON | Sales Tax Invoice | Various branches |  | 20 completed branches | [19 empty] | 100% amount incl. sales tax | In Process
28 | HB Consultant | Commercial Invoice |  | 2024-03-29 | roof structure safety certificate | [19 empty] | payment on roof structure safety certificate submission | Paid
| REON | Sales Tax Invoice |  |  | 8kW Hybrid Inverters | [19 empty] | Paid | Paid
| REON | Sales Tax Invoice |  |  | Additional Panels | [19 empty] | Paid | Paid
[20 empty] | Disbursed |  |  |  | 0 | Incl. of tax payments
[24 empty] | Sr. # | Vendor | On Grid/ | Branch | Branch Name | Amount (PKR) Inclusive Tax
[26 empty] | Hybrid | Code |  | Solar Panel | Invertor | Battery | Local Supplies | Others | Total
[24 empty] | 1 | BEL |  |  |  | 54,201,251 |  |  |  |  | 54,201,251 | ok
[24 empty] | 2 | Reon |  |  |  | 53,676,563 | 47,400,000 | 34,119,681 | 15,387,500 |  | 150,583,744 | ok
[24 empty] | 3 | Pantera |  |  |  | 84,875,567 |  |  | 50,354,720 |  | 135,230,287 | ok
[24 empty] | 4 | AE Solar |  |  |  |  | 93,520,061 |  |  |  | 93,520,061 | ok
[24 empty] | 5 | AICL | [7 empty] | 175,203 | 175,203 | ok
[24 empty] | Total |  |  |  |  | 192,753,381 | 140,920,061 | 34,119,681 | 65,742,220 | 175,203 | 433710546
7693750
20000
441424296
#N/A
|  | Khayaban-e Iqbal Walton Road | [25 empty] | #N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A

## Project Payment Summary
Status: | 2024-08-28 | [5 empty] | Annex-A
Project Payment Summary - Solarization
Vendor | Item | Qty. | Invoice No. | Amount USD | Amount Paid PKR | Payment Date | Payment Description
REON Energy | Solar Panels Canadian Solar N-Type Bi 575Watts | 1740 | REL-MCB-CI-1-11/23 | 10000 | 0 | 2023-12-05 | Processed and Paid
|  |  | 106441 | 10000 | 0 | 2023-12-18 | Processed and Paid
| Solar Panels Canadian Solar N-Type Bi 585Watts (Additionl) | 509 | 107404 | 50000 | 1000000 | 2024-06-10 | Processed and Paid
1000000
| Hybrid Inverters 12 kW Nitrox | 60 | REL-MCB-CI-4-11/23 | 0 | 0 | 2023-11-30 | Processed and Paid
| Hybrid Inverters 08 kW Nitrox | 10 | 107392 | 0 | 5000000 | 2024-06-10 | Processed and Paid
| Hybrid Inverters |  |  |  | 5000000
| Lithium Ion Batteries 48V-100Ah Narada | 120 | REL-MCB-CI-3-11/23 | 200 | 0 | 2023-12-05 | Processed and Paid
|  |  | 106442 | 10 | 0 | 2023-12-19 | Processed and Paid
|  |  | 106424 | 20 | 0 | 2023-12-19 | Processed and Paid
| Batteries |  |  |  | 0
| Local Supplies / Installation | 25 | REL-MCB-CI-5-11/23 | 0 | 0 | 2024-02-07 | Processed and Paid
| Local Supplies / Installation | 25 | REL-MCB-CI-6-02/24 | 0 | 100000 | 2024-03-07 | Processed and Paid
| Local Supplies / Installation | 25 | REL-MCB-CI-7-03/24 | 0 | 0 | 2024-05-06 | Processed and Paid
| Local Supplies / Installation | 9 | REL-MCB-CI-8 | 0 | 100000 | 2024-07-10 | Processed and Paid
| Sub-Total: Local Supplies |  |  |  | 200000
| Total Amount: |  |  |  | 6200000
BEACON Energy | Solar Panels Canadian Solar N-Type Bi 570W | 1800 | BEL-INV/2023/12/2577 | 1000 | 0 | 2024-01-15 | Processed and Paid
| Solar Panels Canadian Solar N-Type Bi 570W (Additional) | [5 empty] | Processed and Paid
| Solar Panels |  |  |  | 0
| Local Supplies / Installation against Completed Branches | 35 | Various | 0 | 1000000 | 2024-05-16 | Processed and Paid
[5 empty] | 0 |  | Processed and Paid
| Sub-Total: Local Supplies |  |  |  | 1000000
| Total Amount: |  |  |  | 1000000
PANTERA Energy | Solar Panels Canadian Solar N-Type Bi 580W (additional) | 700 | 4099 | 10000 | 0 | 2024-03-22 | Processed and Paid
|  |  | 2405 | 5000 |  | 2024-04-24 | Processed and Paid
| Solar Panels |  |  |  | 0
| Solar Panels Canadian Solar N-Type Bi 570W | 2100 | 2084 | 200 | 0 | 2023-11-30 | Processed and Paid
|  |  | 2201 | 10000 | 0 | 2024-02-09 | Processed and Paid
| Solar Panels |  |  |  | 0
| Local Supplies / Installation | 30 | 2085 | 0 | 0 | 2023-12-20 | Processed and Paid
| Branches Payment Cluster-1 | 10 | 2305 (Supplies) 4091 (Services) | 0 |  | 2024-06-26 | Processed and Paid
| Branches Payment Cluster-1 | 3 | 2463 (Supplies) 5081 (Services) | 0 |  | 2024-08-12 | Processed and Paid
| Local Supplies / Installation | 30 | 4095 | 0 | 0 | 2024-03-08 | Processed and Paid
| Local Supplies / Installation | 35 | 5901 | 0 |  | 2024-06-21 | Processed and Paid
| Additional Items CTs | 26 |  | 0 |  |  | Processed and Paid
| Local Supplies |  |  |  | 0
| Total Amount: |  |  |  | 0
AE Solar | On Grid Inverters HUAWEI Sun2000 Series | 160 | 231137 |  |  | 2023-11-30 | Processed and Paid
| On Grid Inverters HUAWEI Sun2000 Series | 40 | 231240 |  |  | 2024-01-15 | Processed and Paid
| On Grid Inverters HUAWEI Sun2000 Series | 28 | 240226 |  |  | 2024-04-03 | Processed and Paid
| On Grid Inverters HUAWEI Sun2000 Series | 5 |  |  |  |  | Processed and Paid
| On Grid Inverters | 200 |  |  | 0
Other - Misc. | HB Consultant | 1 |  |  |  | 2024-05-03 | Processed and Paid
| Solar Junction - Site Inspection | 61 |  |  |  | 2024-05-23 | Processed and Paid
| Al-Fateh Engineering - Site Inspections | 1 |  |  |  |  | Processed and Paid
| Insurance Charges | 0 |  | 0 | 0 | 2024-01-05 | Processed and Paid
| New Age Cables Additional Cable Br 1696 | 1 |  | 0 |  | 2024-07-10 | Processed and Paid
| TOTAL AMOUNT PAID |  |  |  | 7200000 | OK
PANTERA Branches Payment | Branches Payment |  | 2462-2452-2464-5292-2564-2566-2565-5293-2571-2572 |  |  |  | Under Process
BEL Branches Payment | Branchers Payment | 35 |  | 0 |  |  | Under Process
| Branchers Payment | 14 |  | 0 |  |  | Under Process
PANTERA Branches Payment
AE Solar | Return of 30 inverters Supply of 35 inverters Credit Note & Invoice | 35 |  |  |  |  | Under Process
Al Fateh Engineering | Site Inspections | 60 |  |  |  |  | Under Process
Solar Junction | Site Inspections | 20 |  |  |  |  | Under Process
REON Branches Payment | Branchers Payment | 20 |  | 0 |  |  | Under Process
| TOTAL INVOICES IN PROCESS |  |  |  | 0
| TOTAL APPROVED BUDGET |  |  |  | 100000000
| BALANCE AVAILABLE |  |  |  | 92800000